## Review
# | Requirement ID | Topic | Outline | CAL | Method | Requirement text | Technical requirement(s) and tests | SIQ (questions to raise) | Impact and proposal | Testability Finding | Technical Finding | Structure Finding | Traceability Finding | How to test (pseudo-code) | Decision | Decision note | Owner | Date
1 | MVC-119709 | Verify frame tag | 2.2.1.1.4-4 | CAL 2 | Test | The system shall verify the integrity and authenticity of each video frame by comparing the calculated AES-CMAC tag with the 128-bit CMAC tag received in the frame footer. | MVC-106582. Test: CS-SOW1-021. | • SIQ-1 (concept owner, Bosch, Volvo): the Volvo spec says the CMAC is available only from the 18th frame ("the first 17 frames are without the AES-CMAC Tag"). How must SOW2 treat frames 1 to 17: accept as untrusted, drop, or show? Do the 17 frames count from stream start or from the moment the key reaches the imager? • SIQ-2 (Samsung, Bosch): the tag covers only the rows chosen by Start H, Interval H, Total H. Which rows does our concept choose, and is a sparse selection accepted as residual risk? | • Impact: the text says every frame is verified. The imager cannot do that. A tester has no pass criterion for frames 1 to 17, and a reader may think the whole frame is protected. • Proposal: reword to "…each SOW1 video frame that carries an AES-CMAC tag, by comparing the 128-bit tag calculated over the selected rows with the tag received in the frame footer". Add a separate requirement for the frames without a tag. Add that this applies from C1-sample on (the B1/B2-sample settings table in the Volvo spec lists AES-CMAC as "None"). | • The comparison is internal. Only the outcome is visible (accepted, rejected, log entry), which is the same observable as 119710. Proposal: use the security log entry that SRS MVC-108108 already requires as the pass criterion for both. • "Invalid tag" is not defined. Use: one flipped bit in the tag, truncated tag, tag from another session key, all-zero tag, correct tag on modified data. • A test needs the session key to build a valid frame, but 113706 forbids exposing it. With a real imager the tester cannot know the key. A SIM that holds the device private key can decrypt the key that SOW2 sends, so it is the base setup. | • The wording overstates the protection: unselected rows, statistics and other data are not authenticated, and MVC-103033 itself says "selected rows". Record which attacks the sparse selection stops and which not. • Frames 1 to 17 (SIQ-1). • No latency limit for holding a frame until it is verified. The frame-timing analysis (Analysis/SG2_Frame_Timing_Requirements_Analysis.docx) was not checked for one. | • 119709 and 119710 describe one function in two halves, and the SRS has the same pair (MVC-108117, MVC-108116). Merge them, or make the split clear: 119709 defines the comparison, 119710 defines the reaction. • The technical requirement MVC-106582 has exactly the same text. It should say the algorithm (AES-CMAC, 256-bit key, 128-bit tag), the input (rows set by MVC-106576, 108741, 106574, 106583) and that all 128 bits must match. | • Downstream link to MVC-106582 is fine, in both directions. • Upstream: it links to MVC-106231, the same item that the debug and hardware-protection requirements link to, so it is not specific. MVC-106231 is not in the exports. • SRS candidates: 23.2.5.2 (MVC-108122, 108112, 108117), no link in my files. The 17-frame rule is in no requirement. | SIM: build frame N with SSK_sim (decrypted from the key block SOW2 sent), selected rows, valid tag TE-1190: inject frame -> expect: frame passed on (Wireshark: RTP packet appears; log: no CMAC failure) repeat with: tag bit flipped / tag truncated / tag from another key / tag = 0 / data row modified, tag unchanged -> expect: each rejected, log entry "CMAC failed" (UART log) partial match: tag with only first 64 bits right -> expect: rejected Decision: OPEN --- | OPEN
2 | MVC-119710 | Reject frame on failure | 2.2.1.1.4-5 | CAL 2 | Test | The system shall reject any received SOW1 video frame if AES-CMAC verification fails. | MVC-106564. Test: CS-SOW1-022. |  | "Reject" is not defined: dropped, replaced by the previous frame, or shown with a flag? This is a camera that drives a display, so a defined reaction matters. Proposal: state the reaction (drop the frame, count it, log it, keep processing the next frames, which SRS MVC-108105 already says) and when repeated failures start a new session (see 103036). | the observable is the same as 119709. Define it once: dropped frame counter and log event. The VC step "does not cause the same invalid frame to be re-submitted" needs a defined internal buffer to look at. | no limit on how many bad frames are tolerated before the stream is treated as an attack. A single corrupted frame from EMI on the cable would also fail the CMAC (the link has CRC, but the check here is separate). Question: do random corruption and a forged frame get the same reaction? | overlaps 119709 (see entry 1). Overlaps SRS MVC-108116. | MVC-106564 (link both ways). SRS MVC-108116, 108108, 108105. Same upstream as 119709. | SIM: send 10 good frames, 1 frame with wrong tag, 10 good frames Wireshark: RTP shows 20 frames, the bad one missing -> expect: bad frame not forwarded UART log: 1 "CMAC failed" entry -> expect: logged Lauterbach: read dropped-frame counter -> expect: 1 SIM: send 1000 frames, each with a wrong tag -> expect: defined reaction (new session or stay up) once decided Decision: OPEN --- | OPEN
3 | MVC-113705 | Extract tag from footer | 2.2.1.1.4-2 | CAL 2 | Test | The system shall extract the received 128-bit AES-CMAC authentication tag from the embedded footer of each received SOW1 video frame. | MVC-106572. Test: CS-SOW1-019. | where exactly is the footer in the frame (which line, which bytes, byte order) and what is its length when the tag is absent? Defined in the Samsung note (not in the repo). | without the layout the extraction cannot be implemented or tested. Add the layout reference to the technical requirement. | extraction is internal. Either read the extracted value with Lauterbach, or infer it from acceptance, which makes it the same test as 119709. Missing or short footers need a defined reaction (the SRS says reject, MVC-108134). | frame 1 to 17 have no tag (entry 1). The tag is described as 128 bits; whether the footer ever carries more (padding, status bits) is unknown. | this is an implementation step of 119709, not a security property by itself. Proposal: keep it at technical level, or merge into 119709. | MVC-106572. SRS 23.2.5.1 (MVC-108140, 108129, 108134, 108132). | SIM: frame with known tag T = 0x00112233... in the footer Lauterbach: read the extracted-tag buffer -> expect T repeat with 10 different tags -> expect each equal (not hard-coded) SIM: frame without footer / short footer / garbage -> expect: rejected, no crash, log entry Decision: OPEN --- | OPEN
4 | MVC-103033 | Calculate frame CMAC | 2.2.1.1.4-3 | CAL 2 | Test | The system shall calculate a 128-bit AES-CMAC tag over the selected rows of each video frame using the active 256-bit session key. | MVC-106583. Test: CS-SOW1-020. | exactly which bytes form the message: only the pixel and embedded data of the selected rows, or also the line headers/footers and CSI-2 packet bytes? Row numbering base? (Samsung note.) | two implementations could calculate different tags for the same frame. Add the exact message construction and a test vector from Samsung. | a reference calculation (PyRef) works only if the tester knows the SSK and the exact input. With the SIM it is possible. A known-answer test vector from Samsung would make it independent of the SIM. | AES-CMAC with a 256-bit key is standard (NIST SP 800-38B, AES-256). The requirement says "128-bit tag": full output, not truncated, should be stated. The interval rule in MVC-108741 (at least 10 or 30 rows) exists so the imager finishes one row before the next. The host side has no stated rule on how fast it must compute. | it also says "selected rows", which are defined in four other requirements (103055 note, 106576, 108741, 106574). Better to give the row selection its own concept requirement and reference it here. | MVC-106583. SRS MVC-108122, 108121, 108118. | TE-1190: capture a real frame (raw rows) PyRef: tag_ref = AES256-CMAC(SSK, selected rows as defined) SIM: send the frame with tag_ref -> expect: accepted modify 1 byte in a selected row, keep tag_ref -> expect: rejected modify 1 byte in a NOT selected row, keep tag_ref -> expect: accepted (shows the coverage limit, record it) Decision: OPEN --- | OPEN
5 | MVC-103031 | Extract frame counter | 2.2.1.1.4-6 | CAL 2 | Test | The system shall extract the video frame counter from the embedded header data of each received SOW1 video frame and use the counter value for freshness validation. | MVC-113726 (extract) and MVC-106575 (verify freshness, ordering and sequence). Tests: CS-SOW1-025, CS-SOW1-023. | size of the counter (bits), start value, behaviour at wrap-around, and whether the imager resets it at every stream start. (Samsung note.) | the window rule in 113703 cannot be checked at the wrap without the width. Add width and wrap behaviour. | the counter is internal. Read it with Lauterbach. Boundary tests need the SIM to send chosen values, in particular near the maximum. | the counter is only protected by the CMAC if the header line is among the selected rows (start row 0, MVC-106576). If it is not, the counter can be forged freely. State this dependency here. | "extract and use for freshness" is two things, and the concept requirement is satisfied by two technical requirements, one for each. The "use" part (MVC-106575, freshness, ordering and sequence) overlaps MVC-113727, which belongs to 113703 (entry 6). Proposal: keep only the extraction here, and let 113703 own the validity rule. | MVC-113726 and MVC-106575 (CS-SOW1-023 has no entry of its own below, it is covered here and in entry 6). SRS MVC-108099. | SIM: frames with counter 1,2,3,...,N Lauterbach: read extracted counter after each frame -> expect: equal to SIM value SIM: counter = 0xFFFF.. then 0 (width as defined) -> expect: defined wrap handling SIM: header missing / short -> expect: rejected, log entry Decision: OPEN --- | OPEN
6 | MVC-113703 | Freshness window | 2.2.1.1.4-7 | CAL 2 | Test | The system shall reject duplicated, stale, or out-of-order SOW1 video frames based on a 3-frame freshness window and shall accept a frame only when its frame counter satisfies LastAcceptedCounter < ReceivedCounter ≤ LastAcceptedCounter + 3. | MVC-113727. Test: CS-SOW1-026. | counter width and wrap (entry 5). Initial LastAcceptedCounter after a new session. | • Impact: if more than 3 consecutive frames are lost (link problem, brief disturbance, SoC load), every later valid frame has a counter above LastAcceptedCounter + 3 and is rejected. The stream stays dead until a new session. For a safety-relevant camera that is an availability problem. • Proposal: define a recovery: after N consecutive frames rejected only because of the window, but with valid CMAC, re-synchronise LastAcceptedCounter. Or end the session and renegotiate, and say which. | the boundaries in the requirement are good and easy to test with the SIM (equal, lower, +1, +2, +3, +4). Wrap-around and the first frame of a session cannot be tested until they are defined. | • Order of checks: update LastAcceptedCounter only after the CMAC passed. Otherwise a forged frame with a high counter can push the window forward and block genuine frames. State the order. • No behaviour for the first frame of a session. | NONE. | MVC-113727. SRS MVC-108099, 108104, 108102. The recovery behaviour is in no requirement. | SIM: frames with valid CMAC, counters: 10 accepted send 10 (dup) -> reject send 9 (stale) -> reject send 11 -> accept send 13 -> accept (Last=11, +2 ... within +3) send 17 (Last+4) -> reject send frame, counter forged high (valid format, WRONG tag) -> reject, Lauterbach: LastAcceptedCounter unchanged skip 5 frames, then valid CMAC frames -> observe: recovery as defined Decision: OPEN --- | OPEN
7 | MVC-119708 | No trust before session | 2.2.1.1.4-1 | CAL 2 | Test | The system shall not accept SOW1 secured video stream data as trusted before successful SOW1 device authentication and secure session establishment. | MVC-109120. Test: CS-SOW1-024. | what does the system do with video that is "not trusted"? Drop it (no image for the driver) or pass it with an "untrusted" flag? This is a camera for the vehicle; both the safety and security teams must agree. | "not accept as trusted" can be implemented in two very different ways. Define the reaction and who evaluates it (the downstream display side, the vehicle ECU, or SOW2). Cross-check with frames 1 to 17 (entry 1). | the observable is the outgoing stream (Wireshark on RTP) and a status signal if one exists. If "untrusted" is only an internal flag, there is nothing to check from outside. | "secure session establishment" has no definition of when it is complete (imager acknowledgement? first good CMAC?). See entry 17. | NONE. | MVC-109120. SRS MVC-108138. The reaction is in no requirement. | reset, SIM does not answer authentication SIM: send frames (valid CMAC, any key) -> Wireshark: no trusted video out / flagged as untrusted reset, authentication OK, key block not acknowledged -> same terminate session, SIM keeps sending frames of the old session -> rejected complete authentication + session -> Wireshark: video flows Decision: OPEN --- | OPEN
8 | MVC-103063 | Root key in OTP | 2.2.1.1.1-1 | CAL 2 | Test | The system shall store the trusted 2048bit Samsung Root Public Key in OTP memory. | MVC-106562. Test: CS-SOW1-001. | which OTP zone holds it, and who programs it (Mekra factory, Ambarella) and when? The SRS secure-boot requirement mentions OTP "zone 7 [X]" as an open choice. The CV22FS manual describes the power-on-configuration OTP as factory-set and not user-accessible, and I did not find a customer-key zone in the manuals I have. | the test and the production flow depend on the zone. Proposal: name the zone and add "and shall prevent modification, replacement or deletion" (the technical verification criteria already test immutability, the requirement does not state it; SRS MVC-108142 does). | OTP is write-once, so the "cannot be overwritten" test destroys a sample. Test samples need a test root key, because Samsung's private key is not available. A production sample can only be checked by comparing a hash if OTP is read-locked. | the concept says OTP, SRS MVC-108143 says "protected non-volatile storage". Not the same. RSA-2048 public key = 256-byte modulus plus exponent: confirm the free OTP size. | the technical requirement has the same text as the concept requirement. | MVC-106562. SRS 23.2.1 (MVC-108143, 108142, 108144). The secure-boot key (SRS 23.4) is a different root: make sure both are tracked. | Lauterbach: read OTP zone X (if allowed in this lifecycle) -> SHA-256(key) == fingerprint of the Samsung root key Lauterbach/SW: write to OTP zone X -> expect: rejected or locked power cycle + reset -> read again, expect same value SIM signs auth data with the matching private key (test build) -> authentication passes SIM signs with another key -> authentication fails Decision: OPEN --- | OPEN
9 | MVC-107642 | Authenticate imager | 2.2.1.1.2-1 | CAL 2 | Test | The system shall authenticate the Imager by verifying the digital signature received from the Imager over the I2C interface using the provisioned Samsung Root Public Key. | MVC-106561, 106565, 106563. Tests: CS-SOW1-002, 003, 004. | • SIQ-1 (Samsung): define Device_n, KID, Sig_device. The Volvo spec says the signature covers "the device specific RSA public key along with the Device ID". The technical requirement says "over Device_n and KID". Is Device_n the key modulus and KID the Device ID? And is KID a key or algorithm identifier? The SRS (MVC-108135, 108136) lets KID select the signature scheme and hash. | if the signed message is not defined byte for byte, SOW2 and the test cannot agree. Add the exact signed message and encoding to the technical requirement. | needs signed data from the test root key. Negative cases (one field changed, other key) need the SIM. | • The signature in the imager is a fixed value, stored in OTP and read over I2C. I found no challenge-response in the Volvo flow. A fake camera can copy the genuine data (it is not secret) and pass step 2. What stops it is that it does not hold the private key, so it cannot decrypt the session key and cannot produce a valid CMAC. Until the first valid tagged frame (frame 18 or later) SOW2 has no proof that the camera owns the key. Please confirm this is understood and accepted. • The concept fixes the scheme (107641), while the SRS makes KID select the scheme. See entry 10. | the concept requirement is verified by three technical requirements (request, verify, scheme). That is fine, but the pass criteria overlap. Keep each test about one thing. | concept to technical: three links. SRS 23.2.2 and 23.2.3 (MVC-108133, 108131, 108126, 108124, 108113, 108111). | SIM: serve genuine data (Device_n, KID, Sig_device signed by test root) Saleae: capture auth read -> expect: SOW2 asks for the fields; then accepts; key block follows SIM: flip 1 bit in Device_n / KID / Sig_device (one run each) -> expect: rejected, no key block sent SIM: signature from another key -> expect: rejected SIM: copy genuine data, no private key (replay) -> expect: auth accepted, but no valid CMAC frame ever -> frames rejected Decision: OPEN --- | OPEN
10 | MVC-107641 | RSASSA-PSS with SHA-256 | 2.2.1.1.2-2 | CAL 2 | Test | The system shall use RSASSA-PSS with SHA-256 to verify the Imager's digital signature. | MVC-106563 (no link back in Polarion). Test: CS-SOW1-004. | PSS parameters: salt length, mask generation function (MGF1 with SHA-256?). And the SRS lets KID choose scheme and hash (MVC-108135, 108120). Is PSS with SHA-256 the only supported one? | if only one scheme exists, tell the SRS to drop the selection by KID. If KID selects among several, this requirement must say which values of KID are accepted. | partly an inspection (the technical verification criteria say "implementation inspection"). The black-box part: signatures made with PKCS#1 v1.5, other hashes or other salt lengths must fail. The salt-length case cannot be written until the salt is defined. | salt length, MGF and exponent are not stated. | it is a property of the verification in 107642, not a stand-alone behaviour. Proposal: merge into 107642 or keep as a technical detail. | the technical requirement MVC-106563 does not link to it (only to 107642). Add the link. SRS MVC-108120, 108135, 108136. | Code review: verify call = RSASSA-PSS + SHA-256 (CS-SOW1-004 step 1) PyRef: sign (Device_n¦¦KID) with test root key: PSS+SHA-256 -> SIM serves -> expect: accepted PKCS#1 v1.5 -> expect: rejected PSS+SHA-1 or SHA-384 -> expect: rejected PSS+SHA-256, other salt length -> expect: as defined (once the salt is fixed) Decision: OPEN --- | OPEN
11 | MVC-103053 | Retry authentication | 2.2.1.1.2-3 | CAL 2 | Test | The system shall retry the Imager authentication process up to three times if the expected authentication data is failed to be received. | MVC-106566. Test: CS-SOW1-005. | three retries (4 requests) or three attempts (3 requests)? MVC-106569 says "three authentication attempts". One number is needed. Also the timeout per attempt and the time between attempts. | a test that counts requests on the bus cannot pass or fail without it. Proposal: "N attempts in total, each with timeout T". | counting requests with Saleae is easy. Withholding the answer needs the SIM or a way to cut the I2C response. Timing cannot be checked until T exists. | what is "not received": no ACK, partial answer, timeout, or malformed? A complete but invalid answer is a signature failure (reject at once?). Define. | the retry rule is split over two requirements (103053 retry, 103051 terminate) that use different words ("up to three retries" and "configured maximum"). | MVC-106566. SRS MVC-108124, 108126. | SIM: do not answer the authentication read; reset Saleae: count auth read requests until SOW2 stops -> expect: N (as decided) SIM: answer correctly on request 2 -> expect: authentication continues Saleae: measure time between requests -> expect: equals T (once defined) Decision: OPEN --- | OPEN
12 | MVC-103051 | Terminate authentication | 2.2.1.1.2-4 | CAL 2 | Test | The system shall terminate the Imager authentication process if authentication is not successfully completed within the configured maximum number of retry attempts | MVC-106569. Test: CS-SOW1-006. | after termination, what does the ECU do: stay without video, try again later, or enter a safe state? And when is another attempt allowed (only after reset?). | this is a cybersecurity failure that can switch off a camera image. Define the system reaction together with the FuSa team. Proposal: add the reaction and the rule for a later new attempt. | the end state (UNAUTHENTICATED, no key sent, no trusted video) is observable with Lauterbach, Saleae and Wireshark. "Does not retry indefinitely" needs a long observation time (define it). | the concept says "configured maximum", the technical requirement says a fixed "three". Fixed or configurable, and where is it configured? | see 103053. | MVC-106569. SRS MVC-108124 (terminate if data incomplete) is similar but not the same. | SIM never gives valid data; reset Saleae: wait 60 s after the last retry -> expect: no further auth requests, no key write Lauterbach: read auth state -> expect: UNAUTHENTICATED SIM then sends frames with a valid tag -> expect: still rejected (see 119708) Power cycle -> expect: a new authentication attempt starts Decision: OPEN --- | OPEN
13 | MVC-103040 | Extract device public key | 2.2.1.1.3-1 | CAL 2 | Test | Following successful authentication, The system shall extract 2048-bit device public key from the Imager's authentication data. | MVC-106577. Test: CS-SOW1-012. | format of the key in the data (modulus only, fixed exponent?). | add sanity checks (length 2048 bits, odd modulus, exponent as defined) before the key is used. | the extracted key is internal. Indirect check: SOW2 encrypts with it, and the SIM decrypts with its private key. If decryption works, the right key was used. Wrong-size or malformed keys signed with the test root key are easy to create. | the key is covered by the signature only if Device_n is the key modulus (SIQ in entry 9). If it is not covered, a key swap is possible. | NONE. | MVC-106577. SRS 23.2.4.4 (MVC-108153) uses "the authenticated SOW1 Device public key". | SIM: device key K1, signed by test root; authentication OK SIM: decrypt the key block that SOW2 writes with K1_priv -> expect: success (proves K1 was used) SIM: key of 1024 or 4096 bits, valid signature -> expect: rejected, no key block sent SIM: truncated or all-zero key, valid signature -> expect: rejected Lauterbach (optional): compare the key buffer with K1 Decision: OPEN --- | OPEN
14 | MVC-103057 | Generate 256-bit SSK | 2.2.1.1.3-2 | CAL 2 | Test | The system shall generate a 256-bit cryptographically random session key (SSK) following successful Imager authentication. | MVC-106568. Test: CS-SOW1-010. |  | "new key for every session" is in the verification criteria but not in the requirement text. Add it (SRS MVC-108110 says it). | the SSK is only visible through the SIM (decrypting the key block). With a real imager it cannot be seen. Randomness cannot be proven by test, only checked for repeats. | NONE. | overlaps 103042 (how it is generated) and 103036 (new session needs a new key). Proposal: keep "256-bit, new each session" here and "how" in 103042. | MVC-106568. SRS MVC-108107, 108110. | loop 1000 times: reset -> authenticate -> SIM decrypts the key block -> store SSK check: length = 32 bytes; no two SSKs equal; bit balance roughly 50 percent SIM fails authentication -> Saleae: no key block is written Decision: OPEN --- | OPEN
15 | MVC-103042 | CSPRNG and TRNG | 2.2.1.1.3-3 | CAL 2 | Test | The system shall use a CSPRNG compliant with NIST SP 800-90A and seeded by a hardware TRNG to generate the 256-bit session key. | MVC-106560. Test: CS-SOW1-011. | which DRBG and which TRNG interface is used, and is there evidence for SP 800-90A conformity and for the quality of the TRNG? | "compliant with SP 800-90A" is a design property, not testable from outside. Proposal: change the method to Review (design and code evidence), and keep a test only for the failure behaviour. | black-box tests can only show uniqueness. Failure injection (TRNG returns an error) can be done by forcing the return value with Lauterbach. | SP 800-90A defines the DRBG, not the entropy source (SP 800-90B). Reseeding is not mentioned. Proposal: add a reseed rule. | overlaps the debug requirement MVC-103050 (also TRNG). Both depend on the same driver. | MVC-106560. SRS MVC-108106, 108109. Also SRS 23.1.1.2 (DTLS) uses the same source. | Review: CSPRNG library = SP 800-90A DRBG? seed source = SoC TRNG API? -> collect evidence Lauterbach: breakpoint on TRNG read, force error -> expect: session aborted, no key block on I2C (Saleae) collect 1000 SSKs via SIM -> expect: no repeat Decision: OPEN --- | OPEN
16 | MVC-103055 | Encrypt SSK and Row_info | 2.2.1.1.3-4 | CAL 2 | Test | The system shall encrypt the session key and selected row information using the 2048-bit device public key with RSAES-OAEP and SHA-256. (Note: row information format is defined by Samsung, chapter 5 Key sharing of the S5K3B6SA cybersecurity application note.) | MVC-106580, 106576, 108741, 106574. Tests: CS-SOW1-013, 007, 008, 009. | message layout (SSK, Row_info_00, Row_info_01, sizes, order), OAEP label (empty?) and MGF1 hash. The Samsung note is not in the repo. | the layout is needed by implementation and test. Proposal: put the layout in the technical requirement. | OAEP is randomised, so two encryptions of the same input differ. Compare plaintexts only: the SIM decrypts and checks the content. Injecting a known SSK needs a test hook (Lauterbach write before the encrypt call). | capacity check: RSA-2048 with OAEP and SHA-256 carries at most 256 − 2×32 − 2 = 190 bytes, so a 32-byte key plus the row information fits if the row information is small. The row rules in the technical requirements (start 0 or 1, interval at least 10 or 30 by output mode, and the formula start + 1 + (interval + 1) × (total − 1) ≤ ysize_image + ysize_embedded_data) depend on the output mode, so the mode must be known to the code that builds Row_info. | one concept requirement is satisfied by four technical requirements, three of which are about row selection and not about encryption. Proposal: a separate concept requirement for the row selection rules. | MVC-106580, 106576, 108741, 106574. SRS MVC-108153, 108145, 108165, 108166. | SIM (holds device private key): read the key block from I2C (Saleae / TE-1190) PyRef: RSA-OAEP decrypt, SHA-256, MGF1-SHA-256 -> expect plaintext = SSK(32 B) ¦¦ Row_info_00 ¦¦ Row_info_01 Lauterbach: read the Row_info SOW2 used -> expect: equal to the decrypted Row_info decrypt with another private key -> expect: fails Saleae: search the bus capture for the SSK bytes -> expect: not found in plaintext Row rules (one run each): start 2 / interval 9 in RAW12 / total too large (formula +1 row) -> expect: configuration refused Decision: OPEN --- | OPEN
17 | MVC-103034 | Transmit encrypted SSK | 2.2.1.1.3-5 | CAL 2 | Test | The system shall transmit the 2048bit Encrypted Session Key and row information to the Imager for secure session establishment. | MVC-106578. Test: CS-SOW1-014. | how does SOW2 learn that the imager accepted the key block? What is "the expected response" used in 103046? | no requirement says when a session counts as established. Without it 119708, 103046 and 103044 cannot be tested. Proposal: add one requirement, for example "the session is established when the imager acknowledges the key block and the first valid tagged frame is received". | capturing the write on the SoC to deserializer I2C bus is possible. The message layout comes from the Samsung note. | the Volvo spec configures "I2C CRC ON" for the C1-sample, so the transfer is protected by CRC at transport level. The key block of about 256 bytes may need several I2C writes: partial writes need a defined reaction. | the concept says "transmit ... to the Imager", the technical requirement adds "over the I2C interface". Fine. | MVC-106578. SRS MVC-108146, 108145. | Saleae: after authentication OK, capture the writes to the imager key register(s) -> expect: encrypted block, correct length check order: auth read -> verify -> key write (no key write before auth OK) SIM acknowledges -> Lauterbach: state = SESSION_ACTIVE SIM stays silent -> state != SESSION_ACTIVE Decision: OPEN --- | OPEN
18 | MVC-113706 | Do not expose SSK | 2.2.1.1.3-6 | CAL 2 | Test | The system shall not expose the active session key through any accessible interface during the active secure session. | MVC-106571. Test: CS-SOW1-015. |  | "any accessible interface" must be a list. Proposal: UART, JTAG (when unlocked), logs, SOME/IP and DTLS diagnostics, memory dumps, I2C, SPI flash. | a negative test. It needs a list of interfaces and the SSK value (from the SIM) to search for. | the SRS keeps the key in DRAM (MVC-108164). An authorised debug session (secure debug requirements) lets Lauterbach read DRAM, so the key would be readable through the debug interface. Either the debug unlock must exclude the key region, or this is an accepted exception. Please decide. | the technical requirement duplicates the text. SRS has related requirements (MVC-108164, 108163, 108154, 108157). | MVC-106571. SRS MVC-108164, 108163, 108154, 108157. Related to the debug requirements and to DRAM protection (SRS 23.5). | SIM: get SSK value (decrypt the key block) JTAG locked: attach with Lauterbach -> expect: denied search captures for the SSK bytes: I2C (Saleae), Ethernet (Wireshark), UART log -> expect: not found trigger failures (bad frame, failed session) -> read logs and diagnostic responses -> expect: no key bytes authorised debug unlocked: Lauterbach read of the key region in DRAM -> record result; expect: blocked, or an accepted exception Decision: OPEN --- | OPEN
19 | MVC-103046 | Retry session establishment | 2.2.1.1.3-7 | CAL 2 | Test | The system shall retry secure session establishment up to three times if the expected response is failed to be received. | MVC-106567. Test: CS-SOW1-016. | what is the "expected response"? Timeout per try? On each retry, is the same encrypted block sent again, or a new SSK and a new block? | define response, timeout and what is sent again. Proposal: a new block (re-encrypted) with the same SSK, or a new SSK, but state it. | counting retries with Saleae, SIM withholding the response. Nothing can be checked until the response is defined (entry 17). | "three retries" is consistent with 103044 and with the technical requirements. | NONE. | MVC-106567. SRS MVC-108149 (timeout or retry limit). | SIM: accept authentication, do not answer the key block Saleae: count key block writes -> expect: 1 + 3 (as decided) SIM: answer on the 2nd write -> expect: session established Decision: OPEN --- | OPEN
20 | MVC-103044 | Terminate session establishment | 2.2.1.1.3-8 | CAL 2 | Test | The system shall terminate secure session establishment if a secure session is not successfully established after three retry attempts. | MVC-106581. Test: CS-SOW1-017. | the reaction after termination (no video, new full authentication later, safe state). Same question as entry 12. | define what happens next and whether the three retries are repeated after a full new authentication. | the end state is observable: no active session, no more writes, the key not used. | the SRS says partially established session data must be invalidated (MVC-108149). Check that the SSK from the failed attempt is erased, with Lauterbach reading the key buffer. | NONE. | MVC-106581. SRS MVC-108149, 108158. | SIM: never acknowledges the key block Saleae: after the last retry, wait 60 s -> expect: no more key writes Lauterbach: session state = INACTIVE; read key buffer -> expect: zeroed SIM sends tagged frames -> expect: rejected trigger a new attempt (reset) -> expect: authentication starts again Decision: OPEN --- | OPEN
21 | MVC-103036 | New session after triggers | 2.2.1.1.3-9 | CAL 2 | Test | The system shall require establishment of a new secure session, including full SOW1 authentication and generation of a new session key (SSK), after session expiry, system reset, system restart, session termination, or detection of a security failure. | MVC-106573. Test: CS-SOW1-018. | • Session lifetime: what is the expiry time? No requirement defines it. • "Security failure": which events (one bad CMAC frame? ten? an I2C error?). SRS MVC-108158 says "video authentication failure requiring session recovery", which has no definition either. • "System reset" and "system restart": what is the difference? | two of the five triggers cannot be tested without these definitions. This also conflicts with 119710 (reject the frame and continue, SRS MVC-108105): the line between "reject one frame" and "start a new session" is missing. Proposal: define a lifetime, a failure threshold (for example N bad frames within T seconds) and merge reset and restart. | each trigger can be tested alone, as the verification criteria already say. Old key must be rejected afterwards: the SIM keeps sending frames with the old key. | renegotiating while the camera streams: what happens to the video during the new authentication? Interruption time is not limited. | several requirements in one (five triggers). Consider one requirement per trigger group, or keep it and give each trigger its own test (the technical test does this). | MVC-106573. SRS MVC-108156, 108158, 108151. | for trigger in [expiry, reset, restart, termination, security failure]: establish session; SIM sends frames with SSK_old -> accepted fire the trigger Saleae: new auth read + new key block -> expect: yes SIM decrypts the new block: SSK_new != SSK_old SIM sends frames with SSK_old -> expect: rejected Decision: OPEN --- | OPEN
22 | MVC-119714 | No commands before authentication | 2.2.1.1.5-1 | CAL 2 | Test | The system shall not transmit SOW1 control commands before successful SOW1 device authentication. | MVC-109119 ("protected SOW1 control commands"). Test: CS-SOW1-027. | which commands are "control commands"? The imager has to be configured over I2C (for example the settings files in SOW1/Imager Settings/) and the authentication itself is I2C traffic. Which I2C writes are allowed before authentication? | read literally, the requirement forbids the writes needed to start the camera. The technical text says "protected" commands, the SRS too. Proposal: list the protected commands, or list the allowed pre-authentication ones, and use the word "protected" at concept level. | Saleae can list all writes to the imager address. The pass criterion needs the list from the SIQ. | the Volvo spec does not mention any protected command channel. See entry 23. | concept says "SOW1 control commands", technical says "protected SOW1 control commands": two terms. | MVC-109119. SRS MVC-108169. | reset; SIM does not complete authentication trigger a protected command (command source to confirm) Saleae: list all I2C writes to the imager -> expect: only the allowed pre-auth writes, no protected command repeat after authentication failure and before the key block was acknowledged complete authentication + session; trigger again -> expect: command sent Decision: OPEN --- | OPEN
23 | MVC-113701 | CMAC over each command | 2.2.1.1.5-2 | CAL 2 | Test | The system shall calculate a 128-bit AES-CMAC over each SOW1 control command using the established 256-bit session key. | MVC-108740. Test: CS-SOW1-028. | does the imager verify a command tag at all? The Volvo spec section 11 does not describe it. SRS MVC-108160 adds the tag "only when protected control command verification is supported by SOW1". What are the command format and the CMAC input? | if the imager does not check it, the tag adds nothing. Proposal: confirm support first. If supported, put the exact input in the requirement (command, counter, order). The SRS says the counter is included before the tag is calculated (MVC-108159), so the counter is covered. The concept does not say it. | the tag can be checked with PyRef from a captured command and the SSK. Whether the imager accepts or rejects a command with a wrong tag cannot be tested if the imager does not check. | the concept says "each command", the SRS says "protected command only when supported". Conflict. | 113701 (calculate), 119707 (append), 113702 (counter) are three steps of one function. Proposal: one requirement for the protected command format: command + counter + CMAC. | MVC-108740. SRS MVC-108160, 108159. | trigger a protected command (to confirm) Saleae: capture the I2C write to the imager -> parse: cmd ¦ counter ¦ tag SIM: get SSK; PyRef: AES256-CMAC(SSK, cmd¦¦counter) -> expect: equals the tag on the bus change one command byte, recompute with the same key -> tag differs if the imager checks: send a command with a wrong tag -> expect: imager rejects it Decision: OPEN --- | OPEN
24 | MVC-119707 | Append tag to command | 2.2.1.1.5-3 | CAL 2 | Test | The system shall append the calculated 128-bit AES-CMAC tag to each SOW1 control command before transmission. | MVC-106570. Test: CS-SOW1-029. | the field order and size inside the I2C write. The Volvo spec sets I2C CRC ON for the C1-sample: where does the CRC go relative to the tag? | define the frame layout. Proposal: put it in the technical requirement with an example. | easy with Saleae once the layout is defined. | if CMAC generation fails, the command must not be sent (SRS MVC-108160). The concept does not say it. Add it. | see 113701. The concept verification text says only "transmitted command contains the original command data"; the technical text checks field order and encoding. | MVC-106570. SRS MVC-108160. | Saleae: capture a protected command write -> expect: [cmd][counter][16-byte tag] in the defined order Lauterbach: force CMAC calculation to fail -> expect: no command is transmitted repeat for 3 different commands Decision: OPEN --- | OPEN
25 | MVC-113702 | Command counter | 2.2.1.1.5-4 | CAL 2 | Test | The system shall include a monotonically increasing Counter in each SOW1 control command transmitted. | MVC-109121. Test: CS-SOW1-030. | counter width, start value, behaviour at the maximum, and does the imager check it? | "monotonically" allows equal values. Proposal: "strictly increasing" and no reuse within the session (SRS MVC-108161). The counter restarts with each session because the key changes: say so. State the wrap rule (new session before wrap). | with Saleae the counter can be read from many commands. The maximum value case needs a test hook to preset the counter. | replay protection exists only if the imager rejects old counters. If it does not check, the counter protects nothing. Same open point as 113701. | see 113701. | MVC-109121. SRS MVC-108159, 108161. | send 100 protected commands; Saleae: read counter of each -> expect: strictly increasing, no repeats reset (new session) -> counter restarts as defined Lauterbach: preset counter near the max; send commands -> expect: defined behaviour (new session before wrap) if the imager checks: replay an old command (old counter) -> expect: rejected Decision: OPEN --- | OPEN

## Key decisions
# | Topic | Where | Why it matters | Decision | Owner
1 | Frames 1 to 17 have no tag | 119709, 119708, 103033 | Pass/fail is undefined and the text contradicts the Volvo spec | OPEN
2 | Retry versus attempt count | 103053, 103051 | Cannot count I2C requests without one number | OPEN
3 | Reaction to a failure (video off? safe state?) | 119710, 119708, 103051, 103044 | A cybersecurity failure can switch off a camera image | OPEN
4 | Freshness window can dead-lock the stream | 113703 | More than 3 lost frames blocks all later valid frames | OPEN
5 | Static signature, no challenge | 107642 | A copied authentication record passes step 2. Only the CMAC proves the private key, from frame 18 on | OPEN
6 | Session lifetime and "security failure" are undefined | 103036 | Two of five triggers are untestable | OPEN
7 | Do protected commands exist? | 119714, 113701, 119707, 113702 | The Volvo spec has none. The imager may not check them | OPEN
8 | Authorised debug can read the session key from DRAM | 113706 | Conflicts with the "no exposure" requirement | OPEN
9 | Samsung documents and a test root key | all | Without them the message layouts and the valid signatures cannot be produced | OPEN