## Cover
Safety Case Appendix
Purpose
This document serves as an appendix to the functional safety case according to the requirements of ISO26262:2018, listing the evidenace of functional safety work products. It can also be used to track the progress of the planned functional safety work products.
History
Version | Author | Date | Status | Description
0.1 | Mohamed Elbeih | 2026-03-05 | Draft | Initial version
0.2 | Mohamed Elbeih | 2026-06-28 | Draft | Added resp. party, updated time points after 4-way RASIC definition and input from Niklas Hügel

## WP Tracking
| WP | ISO WP | Customer WP | Reusability | Status | Maturity [%] | Doc # | Version | Location | Due phase | Time point | Planned time | Dependency | Resp. Role | Resp. Party | Remarks
Management of functional safety & supporting processes
| Impact Analysis | ISO [2-6.5.1/2] | Volvo QDPR 8. (6.1) | New | OK | 100 | D032847 | 1.0 | D032847/a Functional Safety_Impact analysis_SOW2 (Functional Safety) | Phase A | CW08/2026 |  |  | FSM | ML
| Impact Analysis Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | OK | 100 | D032847 | 2.0 | D032847/Functional Safety_Confirmation Review_Impact analysis_Rev 2 0_SOW2 | Phase B | CW10/2026 |  | Impact Analysis | FSM | ML
| Safety Plan | ISO [2-6.5.3] | Volvo QDPR 8. (6.3) | New | DEV | 80 |  |  |  | Phase B | CW25/2026 |  |  | FSM | BS | Needs update for Series Stream
| Safety Plan Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase C | CW35/2026 |  | Safety Plan | FSM | BS
| Safety Case | ISO [2-6.5.4] | Volvo QDPR 8. (6.14) | New | DEV | 20 |  |  |  | Phase D | CW10/2027 |  |  | FSM | BS | Needs update for Series Stream
| Safety Case Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase D | CW12/2027 |  | Safety Case | FSM | BS
| Functional Safety Audit Report | ISO [2-6.5.5] | Volvo QDPR 8. (7.2) | New | NY | 0 |  |  |  | Phase D | CW15/2027 |  |  | FSA | BS
| Functional Safety Assessment Plan | ISO [2-6.5.5] | Volvo QDPR 8. (7.3) | New | DEV | 80 |  |  |  | Phase B | CW30/2026 |  | Safety Plan | FSA | BS
| Functional Safety Assessment Report | ISO [2-6.5.5] | Volvo QDPR 8. (7.3) | New | NY | 0 |  |  |  | Phase D | CW15/2027 |  |  | FSA | BS
| Release for Production Report | ISO [2-6.5.6] |  | New | NY | 0 |  |  |  | Phase D | CW27/2027 |  | Safety Case | FSM | BS
Concept Phase
| Item Definition | ISO [3-5.5.1] | Volvo QDPR 8. (6.4) | New | NA | 100 |  |  |  | Phase A | CW08/2026 |  |  | OEM | OEM
| Hazard Analysis | ISO [3-6.5.1] | Volvo QDPR 8. (6.5) | New | NA | 100 |  |  |  | Phase A | CW08/2026 |  |  | OEM | OEM
| Functional Safety Concept – Item | ISO [3-7.5.1] | Volvo QDPR 8. (6.6) | New | NA | 100 |  |  |  | Phase A | CW08/2026 |  |  | OEM | OEM
| Safety Goals - SOW2 |  |  | New | DEV | 80 |  |  |  | Phase A | CW25/2026 |  |  | FSE | ML
| Functional Safety Concept – SOW2 | ISO [3-7.5.1] | Volvo QDPR 8. (6.6) | New | DEV | 80 |  |  |  | Phase A | CW25/2026 |  |  | FSE | ML
| Functional Safety Concept - SOW2 Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase B | CW30/2026 |  | FSC - SOW2 | FSM | BS
System Level
| Technical Safety Concept (TSC) – incl. architectural design, technical safety requirements | ISO [4-6.5.1/2/3] | Volvo QDPR 8. (6.7) | New | DEV | 50 |  |  |  | Phase B | CW31/2026 | CW17/2026 | FSC, logical arch. | FSE | ML/BS | Pending approvals Platform requirements targeting CW23 SG requirements targeting CW31
| Hardware-Software Interface (HSI) Specification | ISO [4-6.5.4] ISO [5-6.5.2] ISO [6-6.5.2] | Volvo QDPR 8. (6.7) | New | DEV | 30 |  |  |  | Phase B | CW31/2026 | CW17/2026 |  | FSE | ML/BS
| Specification of requirements for production, operation, service and decommissioning | ISO [4-6.5.5] | Volvo QDPR 8. (6.7) | New | DEV | 80 |  |  |  | Phase B | CW31/2026 | CW17/2026 |  | FSE | ML
| SAD+HSI+POSD+TSC Verification Review | ISO [4-6.5.6] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase B | CW31/2026 | CW17/2026 | TSC | FSE | ML
| Technical Safety Concept Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase C | CW35/2026 |  | TSC | FSM | BS
| System FMEA (Component FMEA) | ISO [4-6.5.7] | Volvo QDPR 8. (6.10) | New | DEV | 40 |  |  |  | Phase C | CW31/2026 | CW17/2026 | Sys. req, logical/physicalarch. | ML FSE | ML | Check sys FMEA is done on physical architecture. In that case tailoring can be done to skip safety HW FMEA Update from Miro 23-04
| System FMEA Verification Review | ISO [9-8.5.2] | Volvo QDPR 8. (6.12) | New | DEV | 40 |  |  |  | Phase C | CW31/2026 | CW17/2026 | System FMEA | ML FSE | ML | FMEA is verified during MEKRA meetings. No records
| System FMEA Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase C | CW35/2026 |  | System FMEA | FSM | BS
| System FTA | ISO [4-6.5.7] | Volvo QDPR 8. (6.10) | New | DEV | 80 |  |  |  | Phase C | CW31/2026 | CW15/2026 |  | FSE | BS
| System FTA Verification Review | ISO [9-8.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW31/2026 | CW16/2026 |  | FSE | BS
| System FTA Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase C | CW35/2026 |  |  | FSM | BS
| System Dependent Failure Analysis | ISO [9-7.5.1] | Volvo QDPR 8. (6.10) | New | DEV | 80 |  |  |  | Phase C | CW31/2026 | CW15/2026 | FTA (or FMEA) | FSE | BS
| System Dependent Failure Analysis Verification Review | ISO [9-7.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW31/2026 | CW16/2026 | System DFA | FSE | BS
| System Dependent Failure Analysis Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase C | CW35/2026 |  | System DFA | FSM | BS
| Integration and test strategy (SYS.4 & SYS.5) | ISO [4-7.5.1] | Volvo QDPR 8. (6.11) | New | NY | 0 |  |  |  | Phase B | CW25/2026 | CW19/2026 |  | FSE | BS | Part of overall system test strategy To check status with BS testing team
| Integration and test strategy Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase C | CW30/2026 |  | Int.&Test Strategy | FSM | BS
| HW-SW Integration and test report (SYS.4) | ISO [4-7.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase D | CW52/2026 |  | TSC | Test | ML/BS => More detaills needed as in RASIC | Verification of TSR's (Level 45 Polarion)
| System Integration and test report (SYS.5) | ISO [4-7.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase D | CW09/2027 |  | FSC | Test | ML/BS => More detaills needed as in RASIC | Verification of FSR's (Level 25 Polarion)
| Vehicle Integration and test report (VAL.1) | ISO [4-7.5.2] | Volvo QDPR 8. (6.12) | New | NA | 100 |  |  |  | Phase D | N/A |  |  | OEM | OEM
| Safety validation specification (VAL.1) | ISO [4-8.5.2] | Volvo QDPR 8. (6.12) | New | NA | 100 |  |  |  | Phase D | N/A |  |  | OEM | OEM
| Safety validation specification Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NA | 100 |  |  |  | Phase D | N/A |  |  | OEM | OEM
| Safety validation report | ISO [4-8.5.2] | Volvo QDPR 8. (6.12) | New | NA | 100 |  |  |  | Phase D | N/A |  |  | OEM | OEM
| MEKRA Joint Review 1 (consistency check) | - | - | New | NY | 0 |  |  |  |  | CW44/2026 |  |  | FSE | ML
| MEKRA Joint Review 2 (consistency check) | - | - | New | NY | 0 |  |  |  |  | CW06/2027 |  |  | FSE | ML
| MEKRA Joint Review 3 (consistency check) | - | - | New | NY | 0 |  |  |  |  | CW17/2027 |  |  | FSE | ML
Hardware Level
| Hardware Safety Requirements Specification (HWSRS) | ISO [5-6.5.1] | Volvo QDPR 8. (6.8) | New | DEV | 30 |  |  |  | Phase B | CW34/2026 | CW17/2026 | TSC incl. temp sensing req's | FSE | BS | Will be revisited after TSC req's are approved
| Hardware-software interface (HSI) specification (refined) | ISO [5-6.5.2] |  | New | NY | 0 |  |  |  |  | CW34/2026 |  |  | FSE | BS/ML
| Hardware safety requirements verification report | ISO [5-6.5.3] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase B | CW34/2026 | CW18/2026 | HWSRS | FSE | BS
| Hardware design specification | ISO [5-7.5.1] |  | New | DEV | 50 |  |  |  | Phase B | CW36/2026 | CW19/2026 |  | HW | ML
| Hardware design verification report | ISO [5-7.5.3] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase B | CW36/2026 | CW19/2026 | HW design | HW | ML
| Qualitative HW Safety Analysis (HW FMEA) | ISO [5-7.5.2] | Volvo QDPR 8. (6.10) | New | NY | 0 |  |  |  | Phase C | CW25/2026 |  |  | HW | - | covered properly with sys. FMEA? To be tailored in Plan
| Quantitative HW Safety Analysis (HW FMEDA) | ISO [5-7.5.2] | Volvo QDPR 8. (6.10) | New | DEV | 45 |  |  |  | Phase C | CW34/2026 |  | HW schematic, TSC | FSE | BS | Will be run in parallel to the C1-Sample order
| Quantitative HW Safety Analysis (HW FMEDA) Verification Review | ISO [9-8.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW34/2026 |  |  | FSE | BS/ML
| Quantitative HW Safety Analysis (HW FMEDA) Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase C | CW39/2026 |  |  | FSM | BS
| Analysis of the effectiveness of the architecture of the item to cope with the random hardware failures | ISO [5-8.5.1] | Volvo QDPR 8. (6.10) | New | DEV | 45 |  |  |  | Phase C | CW34/2026 |  |  | FSE | BS
| Analysis of the effectiveness of the architecture of the item to cope with the random hardware failures Verification Review | ISO [5-8.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW34/2026 |  |  | FSE | BS
| Analysis of safety goal violations due to random hardware failures | ISO [5-9.5.1] | Volvo QDPR 8. (6.10) | New | NY | 0 |  |  |  | Phase C | CW34/2026 |  |  | FSE | BS
| Analysis of safety goal violations due to random hardware failures Verification Review | ISO [5-9.5.3] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW34/2026 |  |  | FSE | BS
| Specification of dedicated measures for hardware | ISO [5-9.5.2] |  | New | NY | 0 |  |  |  | Phase C | CW34/2026 |  |  | FSE | BS | part of FMEDA report?
| Hardware integration and verification specification | ISO [5-10.5.1] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW38/2026 | CW36/2026 | HW sample | HW | ML | Date feasible for ML?
| Hardware integration and verification report | ISO [5-10.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW46/2026 | CW36/2026 |  | HW | ML/BS | Date feasible for ML?
Software Level
| Software Safety Requirements Specification (SWSRS) | ISO [6-6.5.1] | Volvo QDPR 8. (6.9) | New | NY | 0 |  |  |  | Phase B | CW36/2026 | TSC | TSC | FSE | BS |  | According RASIC
| Hardware-software interface (HSI) specification (refined) | ISO [6-6.5.2] |  | New | NY | 0 |  |  |  |  | CW36/2026 |  | TSC | FSE | BS/ML
| Software Verification Report | ISO [6-6.5.3] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase B | CW38/2026 |  |  | FSE | BS
| Software architectural design specification | ISO [6-7.5.1] | Volvo QDPR 8. (6.9) | New | NY | 0 |  |  |  | Phase B | CW36/2026 | TSC | SWSRS | FSE | BS/ML
| Qualitative SW Safety Analysis (SW FMEA) | ISO [6-7.5.2] | Volvo QDPR 8. (6.10) | New | NY | 0 |  |  |  | Phase C | tbc |  |  | SW | BS
| Qualitative SW Safety Analysis (SW FMEA) Verification Review | ISO [9-8.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | tbc |  |  | SW | BS
| Qualitative SW Safety Analysis (SW FMEA) Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase C | tbc |  |  | SW | BS
| Dependent Failure Analysis (SW) | ISO [6-7.5.3] | Volvo QDPR 8. (6.10) | New | NY | 0 |  |  |  | Phase C | tbc |  |  | SW | BS
| Dependent Failure Analysis (SW) Verification Review | ISO [9-7.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | tbc |  |  | SW | BS
| Dependent Failure Analysis (SW) Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase C | tbc |  |  | SW | BS
| Software Verification Report | ISO [6-7.5.4] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C |  |  |  | SW | BS
| Software unit design specification | ISO [6-8.5.1] |  | New | NY | 0 |  |  |  | Phase C | CW40/2026 |  |  | SW | BS
| Software unit implementation | ISO [6-8.5.2] |  | New | NY | 0 |  |  |  | Phase C | CW40/2026 |  |  | SW | BS
| Software unit verification specification (SWE.4) | ISO [6-9.5.1] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW40/2026 |  |  | SW | BS
| Software unit verification report (SWE.4) | ISO [6-9.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW47/2026 |  |  | SW | BS
| Software integration verification specification (SWE.5) | ISO [6-10.5.1] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW40/2026 |  |  | SW | BS
| Software integration verification report (SWE.5) | ISO [6-10.5.3] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW47/2026 |  |  | SW | BS
| Software qualification verification specification (SWE.6) | ISO [6-11.5.1] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW40/2026 |  |  | SW | BS
| Software qualification verification report (SWE.6) | ISO [6-11.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW47/2026 |  |  | SW | BS
| Configuration data specification | ISO [6-C.5.1] |  | New | NY | 0 | [7 empty] | SW
| Calibration data specification | ISO [6-C.5.2] |  | New | NY | 0 | [7 empty] | SW
| Configuration data | ISO [6-C.5.3] |  | New | NY | 0 | [7 empty] | SW
| Calibration data | ISO [6-C.5.4] |  | New | NY | 0 | [7 empty] | SW
| Verification specification (refined) | ISO [6-C.5.5] |  | New | NY | 0 | [7 empty] | SW
| Verification report (refined) | ISO [6-C.5.6] |  | New | NY | 0 | [7 empty] | SW
| Software architectural design specification (refined) | ISO [6-C.5.7] |  | New | NY | 0 | [7 empty] | SW
| Documentation of the software development environment (refined) | ISO [6-C.5.8] |  | New | NY | 0 | [7 empty] | SW
Production, operation, service and decommissioning
| Safety Production and Control Plan | ISO [2-7.5.1] ISO [4-6.5.5] ISO [5-7.5.4] ISO [7-5.5.1 – 4] ISO [7-6.5.1/2] | Volvo QDPR 8. (6.13) | New | NY | 0 |  |  |  | Phase D | CW35/2026 |  | TSC POSD req's | FSM | BS | check APIS documents if compliant with ISO26262, else use BS templates
| Process FMEA | ISO [7-5.4.1] | Volvo QDPR 8. (6.10) | New | NY | 0 |  |  |  | Phase C | CW35/2026 |  | Process documentation | FSE | BS
| Safety Service Plan | ISO [7-5.5.5 – 5.5.10] | Volvo QDPR 8. (6.13) | New | NY | 0 |  |  |  | Phase D | CW50/2026 |  |  | FSM | BS
| Field observation instructions | ISO [7-7.5.1] |  | New | NY | 0 |  |  |  | Phase D | CW50/2026 |  |  | Production | ???
Supporting Processes
| Supplier selection report | ISO [8-5.5.1] |  | New | OK | 100 |  |  |  | Phase A | CW08/2026 |  |  | PM | ML | Supplier seld-assessment (BS)
| Configuration Management plan | ISO [8-7.5.1] |  | New | OK | 100 |  |  |  | Phase A | CW08/2026 |  |  | PM | ML
| Change Management plan | ISO [8-8.5.1] |  | New | DEV | 90 |  |  |  | Phase A | CW08/2026 |  |  | PM | ML
| Verification Plan/Specification/Report | ISO [8-9.5.1 – 3] |  | New | NOK | 0 |  |  |  | Phase A | CW08/2026 |  |  | PM | ML
| Documentation Management Plan | ISO [8-10.5.1] |  | New | NOK | 0 |  |  |  | Phase A | CW08/2026 |  |  | PM | ML
| Software tool criteria evaluation report (Systems+HW levels) | ISO [8-11.5.1] |  | New | NOK | 0 |  |  |  | Phase B | CW10/2026 |  |  | FSM | ML
| Software tool criteria evaluation report (SW level) | ISO [8-11.5.1] |  | New | NOK | 0 |  |  |  | Phase B | CW10/2026 |  |  | FSM | BS
| Software tool qualification report (Systems+HW level) | ISO [8-11.5.2] |  | New | NOK | 0 |  |  |  | Phase B | CW10/2026 |  |  | FSM | ML
| Software tool qualification report SW level) | ISO [8-11.5.2] |  | New | NOK | 0 |  |  |  | Phase B | CW10/2026 |  |  | FSM | BS
| Software component documentation/ qualification report | ISO [8-12.5.1 – 3] |  | New | DEV | 50 |  |  |  | Phase C | CW31/2026 |  |  | FSM | BS | Qualification of SW drivers (SerDes + Image Sensor)
| Hardware element evaluation plan/ test plan and report | ISO [8-13.5.1 – 3] |  | N/A | NA | 100 |  |  |  | N/A | N/A |  |  | N/A | -
| Proven in use argument/analysis report | ISO [8-14.5.1/2] |  | N/A | NA | 100 |  |  |  | N/A | N/A |  |  | N/A | -
Possible Update
Note on E1: Content to be changed in cover-sheet -> Base project ID

## Legend
OK | WP finished
DEV | Work product under development
NOK | Work product not started while due at current project phase
NY | Work product not yet due at current project phase
NA | Not applicable