## Cover
Safety Case Appendix
Purpose
This document serves as an appendix to the functional safety case according to the requirements of ISO26262:2018, listing the evidenace of functional safety work products. It can also be used to track the progress of the planned functional safety work products.
History
Version | Author | Date | Status | Description
0.1 | Mohamed Elbeih | 2026-03-05 | Draft | Initial version
0.2 | Mohamed Elbeih | 2026-06-28 | Draft | Added resp. party, updated time points after 4-way RASIC definition and input from Niklas Hügel
0.3 | Mohamed Elbeih | 2026-07-09 | Draft | Added columns for deliveries
0.4 | Niklas Hügel | 2026-07-23 | Draft | Added comments "ML acceptance" for dedicated WP's Added sheet "Schedule"
0.5 | Niklas Hügel | 2026-08-07 | Draft | Updates on sheet "Schedule"

## WP Tracking
| WP | ISO WP | Customer WP | Reusability | Status | Maturity [%] | Doc # | Version | Location | Due phase | Time point | Planned time | P1 | P2 | P3 | SOP | Dependency | Resp. Role | Resp. Party | Remarks
Management of functional safety & supporting processes
| Impact Analysis | ISO [2-6.5.1/2] | Volvo QDPR 8. (6.1) | New | OK | 100 | D032847 | 1.0 | D032847/a Functional Safety_Impact analysis_SOW2 (Functional Safety) | Phase A | CW08/2026 | [6 empty] | FSM | ML
| Impact Analysis Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | OK | 100 | D032847 | 2.0 | D032847/Functional Safety_Confirmation Review_Impact analysis_Rev 2 0_SOW2 | Phase B | CW10/2026 | [5 empty] | Impact Analysis | FSM | ML
| Safety Plan | ISO [2-6.5.3] | Volvo QDPR 8. (6.3) | New | DEV | 80 |  |  |  | Phase B | CW25/2026 | [6 empty] | FSM | BS | Needs update for Series Stream
| Safety Plan Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase C | CW35/2026 | [5 empty] | Safety Plan | FSM | BS/ML | Incl. ML acceptance
| Safety Case | ISO [2-6.5.4] | Volvo QDPR 8. (6.14) | New | DEV | 20 |  |  |  | Phase D | CW10/2027 | [6 empty] | FSM | BS | Needs update for Series Stream
| Safety Case Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase D | CW12/2027 | [5 empty] | Safety Case | FSM | BS/ML | Incl. ML acceptance
| Functional Safety Audit Report | ISO [2-6.5.5] | Volvo QDPR 8. (7.2) | New | NY | 0 |  |  |  | Phase D | CW15/2027 | [6 empty] | FSA | BS
| Functional Safety Assessment Plan | ISO [2-6.5.5] | Volvo QDPR 8. (7.3) | New | DEV | 80 |  |  |  | Phase B | CW33/2026 | [5 empty] | Safety Plan | FSA | BS
| Functional Safety Assessment Report | ISO [2-6.5.5] | Volvo QDPR 8. (7.3) | New | NY | 0 |  |  |  | Phase D | CW15/2027 | [6 empty] | FSA | BS
| Release for Production Report | ISO [2-6.5.6] |  | New | NY | 0 |  |  |  | Phase D | CW27/2027 | [5 empty] | Safety Case | FSM | BS
Concept Phase
| Item Definition | ISO [3-5.5.1] | Volvo QDPR 8. (6.4) | New | NA | 100 |  |  |  | Phase A | CW08/2026 | [6 empty] | OEM | OEM
| Hazard Analysis | ISO [3-6.5.1] | Volvo QDPR 8. (6.5) | New | NA | 100 |  |  |  | Phase A | CW08/2026 | [6 empty] | OEM | OEM
| Functional Safety Concept – Item | ISO [3-7.5.1] | Volvo QDPR 8. (6.6) | New | NA | 100 |  |  |  | Phase A | CW08/2026 | [6 empty] | OEM | OEM
| Safety Goals - SOW2 |  |  | New | DEV | 80 |  |  |  | Phase A | CW25/2026 |  | CW25/2026 |  |  |  |  | FSE | ML
| Functional Safety Concept – SOW2 | ISO [3-7.5.1] | Volvo QDPR 8. (6.6) | New | DEV | 80 |  |  |  | Phase A | CW25/2026 |  | CW25/2026 |  |  |  |  | FSE | ML
| Functional Safety Concept – SOW2 Verification Review | [16 empty] | FSE | ML
| Functional Safety Concept - SOW2 Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase B | CW30/2026 |  | CW30/2026 |  |  |  | FSC - SOW2 | FSM | BS
System Level
| Technical Safety Concept (TSC) – Technical safety Req | ISO [4-6.5.1/2/3] | Volvo QDPR 8. (6.7) | New | DEV | 50 |  |  |  | Phase B | CW39/2026 | CW17/2026 | CW26/2026 | CW39/2026 |  |  | FSC, logical arch. | FSE | ML/BS | Pending approvals Platform requirements targeting CW23 SG requirements targeting CW31
Verification Review - Technical safety Req
| Technical Safety Concept (TSC) – Architectural design | ISO [4-6.5.1/2/3] | Volvo QDPR 8. (6.7)
Verification Review - Architectural design
Identification of safety mechanism from Amba SW Safety Manual
| Identification of safety mechanism from Amba SW Safety Manual - Verfication Review | [18 empty] | Incl. ML acceptance
| Hardware-Software Interface (HSI) Specification | ISO [4-6.5.4] ISO [5-6.5.2] ISO [6-6.5.2] | Volvo QDPR 8. (6.7) | New | DEV | 30 |  |  |  | Phase B | CW39/2026 | CW17/2026 | CW26/2026 | CW39/2026 |  |  |  | FSE | ML/BS
| Specification of requirements for production, operation, service and decommissioning | ISO [4-6.5.5] | Volvo QDPR 8. (6.7) | New | DEV | 80 |  |  |  | Phase B | CW39/2026 | CW17/2026 | CW26/2026 | CW39/2026 |  |  |  | FSE | ML
| SAD+HSI+POSD+TSC Verification Review | ISO [4-6.5.6] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase B | CW39/2026 | CW17/2026 | CW26/2026 | CW39/2026 |  |  | TSC | FSE | ML/BS | Incl. ML acceptance
| Technical Safety Concept Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase C | CW43/2026 |  |  | CW43/2026 |  |  | TSC | FSM | BS
| System FMEA (Component FMEA) | ISO [4-6.5.7] | Volvo QDPR 8. (6.10) | New | DEV | 40 |  |  |  | Phase C | CW36/2026 | CW17/2026 |  |  |  |  | Sys. req, logical/physicalarch. | ML FSE | ML | Check sys FMEA is done on physical architecture. In that case tailoring can be done to skip safety HW FMEA Update from Miro 23-04
| System FMEA Verification Review | ISO [9-8.5.2] | Volvo QDPR 8. (6.12) | New | DEV | 40 |  |  |  | Phase C | CW36/2026 | CW17/2026 |  |  |  |  | System FMEA | ML FSE | ML | FMEA is verified during MEKRA meetings. No records
| System FMEA Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase C | CW38/2026 | [5 empty] | System FMEA | FSM | BS
| System FTA | ISO [4-6.5.7] | Volvo QDPR 8. (6.10) | New | DEV | 80 |  |  |  | Phase C | CW31/2026 | CW15/2026 | [5 empty] | FSE | BS
| System FTA Verification Review | ISO [9-8.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW31/2026 | CW16/2026 | [5 empty] | FSE | BS/ML | Incl. ML acceptance
| System FTA Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase C | CW35/2026 | [6 empty] | FSM | BS
| System Dependent Failure Analysis | ISO [9-7.5.1] | Volvo QDPR 8. (6.10) | New | DEV | 80 |  |  |  | Phase C | CW31/2026 | CW15/2026 |  |  |  |  | FTA (or FMEA) | FSE | BS
| System Dependent Failure Analysis Verification Review | ISO [9-7.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW31/2026 | CW16/2026 |  |  |  |  | System DFA | FSE | BS/ML | Incl. ML acceptance
| System Dependent Failure Analysis Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase C | CW35/2026 | [5 empty] | System DFA | FSM | BS
| Integration and test strategy (SYS.4 & SYS.5) | ISO [4-7.5.1] | Volvo QDPR 8. (6.11) | New | NY | 0 |  |  |  | Phase B | CW25/2026 | CW19/2026 | [5 empty] | FSE | BS | Part of overall system test strategy To check status with BS testing team
| Integration and test strategy Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase C | CW30/2026 | [5 empty] | Int.&Test Strategy | FSM | BS/ML | Incl. ML acceptance
| HW-SW Integration and test report (SYS.4) System Integration and test report (SYS.4) | ISO [4-7.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase D | [6 empty] | TSC | Test | BS | Verification of TSR's (Level 45 Polarion)
| Specification |  |  | New | NY | 0 |  |  |  |  | CW43/2026 |  | CW32/2026 | CW43/2026 |  |  |  | Test | BS
| Specification Verification Review | [9 empty] | CW43/2026 |  | CW32/2026 | CW43/2026 |  |  |  | Test, FSE | BS/ ML | Incl. ML acceptance
| Execution & reporting |  |  | New | NY | 0 |  |  |  |  | CW04/2027 |  | CW42/2027 | CW04/2027 |  |  |  | Test | BS
| Execution & reporting Verification Review | [9 empty] | CW04/2027 |  | CW42/2026 | CW04/2027 |  |  |  | FSM | ML | Incl. ML acceptance
| Integrated System test report (SYS.5) | ISO [4-7.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase D | [6 empty] | FSC | Test | BS | Verification of FSR's (Level 25 Polarion)
| Specification |  |  | New | NY | 0 |  |  |  |  | CW43/2026 |  | CW32/2026 | CW43/2026 |  |  |  | Test | BS
| Specification Verification Review | [9 empty] | CW43/2026 |  | CW32/2026 | CW43/2026 |  |  |  | Test, FSE | BS/ ML | Incl. ML acceptance
| Execution & reporting |  |  | New | NY | 0 |  |  |  |  | CW04/2027 |  | CW42/2027 | CW04/2027 |  |  |  | Test | BS
| Execution & reporting Verification Review | [9 empty] | CW04/2027 |  | CW42/2026 | CW04/2027 |  |  |  | FSM | ML | Incl. ML acceptance
| Vehicle Integration and test report (VAL.1) | ISO [4-7.5.2] | Volvo QDPR 8. (6.12) | New | NA | 100 |  |  |  | Phase D | N/A | [6 empty] | OEM | OEM
| Safety validation specification (VAL.1) | ISO [4-8.5.2] | Volvo QDPR 8. (6.12) | New | NA | 100 |  |  |  | Phase D | N/A | [6 empty] | OEM | OEM
| Safety validation specification Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NA | 100 |  |  |  | Phase D | N/A | [6 empty] | OEM | OEM
| Safety validation report | ISO [4-8.5.2] | Volvo QDPR 8. (6.12) | New | NA | 100 |  |  |  | Phase D | N/A | [6 empty] | OEM | OEM
| MEKRA Joint Review 1 (consistency check) | - | - | New | NY | 0 |  |  |  |  | CW44/2026 | [6 empty] | FSE | ML
| MEKRA Joint Review 2 (consistency check) | - | - | New | NY | 0 |  |  |  |  | CW06/2027 | [6 empty] | FSE | ML
| MEKRA Joint Review 3 (consistency check) | - | - | New | NY | 0 |  |  |  |  | CW17/2027 | [6 empty] | FSE | ML
Hardware Level
| Hardware Safety Requirements Specification (HWSRS) | ISO [5-6.5.1] | Volvo QDPR 8. (6.8) | New | DEV | 30 |  |  |  | Phase B | CW34/2026 | CW17/2026 | CW26/2026 | CW40/2026 |  |  | TSC incl. temp sensing req's | FSE | BS | Will be revisited after TSC req's are approved
| Hardware-software interface (HSI) specification (refined) | ISO [5-6.5.2] |  | New | NY | 0 |  |  |  |  | CW34/2026 | CW34/2026 | [5 empty] | FSE | BS/ML
| Hardware safety requirements verification report | ISO [5-6.5.3] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase B | CW34/2026 | CW34/2026 |  | CW41/2026 |  |  | HWSRS | FSE | BS/ML | Incl. ML acceptance
| Hardware design specification | ISO [5-7.5.1] |  | New | DEV | 50 |  |  |  | Phase B | CW36/2026 | CW19/2026 | [5 empty] | HW | ML
| Hardware design verification report | ISO [5-7.5.3] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase B | CW36/2026 | CW19/2026 |  |  |  |  | HW design | HW | ML
| Qualitative HW Safety Analysis (HW FMEA) | ISO [5-7.5.2] | Volvo QDPR 8. (6.10) | New | NY | 0 |  |  |  | Phase C | CW25/2026 | [6 empty] | HW | - | covered properly with sys. FMEA? To be tailored in Plan
| Quantitative HW Safety Analysis (HW FMEDA) | ISO [5-7.5.2] | Volvo QDPR 8. (6.10) | New | DEV | 45 |  |  |  | Phase C | CW34/2026 | [5 empty] | HW schematic, TSC | FSE | BS | Will be run in parallel to the C1-Sample order
| Quantitative HW Safety Analysis (HW FMEDA) Verification Review | ISO [9-8.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW37/2026 | [6 empty] | FSE | BS/ML | Incl. ML acceptance
| Quantitative HW Safety Analysis (HW FMEDA) Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase C | CW38/2026 | [6 empty] | FSM | BS
| Analysis of the effectiveness of the architecture of the item to cope with the random hardware failures | ISO [5-8.5.1] | Volvo QDPR 8. (6.10) | New | DEV | 45 |  |  |  | Phase C | CW34/2026 | [6 empty] | FSE | BS | part of FMEDA report
| Analysis of the effectiveness of the architecture of the item to cope with the random hardware failures Verification Review | ISO [5-8.5.2] | Volvo QDPR 8. (6.12) | New | DEV | 45 |  |  |  | Phase C | CW34/2026 | [6 empty] | FSE | BS | part of FMEDA report
| Analysis of safety goal violations due to random hardware failures | ISO [5-9.5.1] | Volvo QDPR 8. (6.10) | New | DEV | 45 |  |  |  | Phase C | CW34/2026 | [6 empty] | FSE | BS | part of FMEDA report
| Analysis of safety goal violations due to random hardware failures Verification Review | ISO [5-9.5.3] | Volvo QDPR 8. (6.12) | New | DEV | 45 |  |  |  | Phase C | CW34/2026 | [6 empty] | FSE | BS | part of FMEDA report
| Specification of dedicated measures for hardware | ISO [5-9.5.2] |  | New | DEV | 45 |  |  |  | Phase C | CW34/2026 | [6 empty] | FSE | BS | part of FMEDA report? To be checked by BS
| Hardware integration and verification specification | ISO [5-10.5.1] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW38/2026 | CW36/2026 |  |  |  |  | HW sample | HW | ML | Date feasible for ML?
| Hardware integration and verification specification Verification Review | [16 empty] | HW, FSE | ML/BS | Incl. ML acceptance
| Hardware integration and verification report | ISO [5-10.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW46/2026 | CW36/2026 | [5 empty] | HW | ML/BS | Date feasible for ML?
| Hardware integration and verification report Verification Review | [16 empty] | FSM | ML | Incl. ML acceptance
Software Level
| Documentation of the software development environment | ISO [6-5.5.1]
| Software Safety Requirements Specification (SWSRS) | ISO [6-6.5.1] | Volvo QDPR 8. (6.9) | New | NY | 0 |  |  |  | Phase B | CW36/2026 | TSC |  |  |  |  | TSC | FSE | BS |  | According RASIC
| Hardware-software interface (HSI) specification (refined) | ISO [6-6.5.2] |  | New | NY | 0 |  |  |  |  | CW36/2026 | [5 empty] | TSC | FSE | BS/ML
| Software Verification Report (Review) | ISO [6-6.5.3] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase B | CW38/2026 | [6 empty] | FSE (SW?) | BS/ML | Incl. ML acceptance
| Software architectural design specification | ISO [6-7.5.1] | Volvo QDPR 8. (6.9) | New | NY | 0 |  |  |  | Phase B | CW36/2026 | TSC |  |  |  |  | SWSRS | FSE | BS/ML
| Qualitative SW Safety Analysis (SW FMEA) | ISO [6-7.5.2] | Volvo QDPR 8. (6.10) | New | NY | 0 |  |  |  | Phase C | tbc | [6 empty] | SW | BS
| Qualitative SW Safety Analysis (SW FMEA) Verification Review | ISO [9-8.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | tbc | [6 empty] | SW | BS/ML | Clarify if ML acceptance is needed?
| Qualitative SW Safety Analysis (SW FMEA) Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase C | tbc | [6 empty] | SW | BS
| Dependent Failure Analysis (SW) | ISO [6-7.5.3] | Volvo QDPR 8. (6.10) | New | NY | 0 |  |  |  | Phase C | tbc | [6 empty] | SW | BS
| Dependent Failure Analysis (SW) Verification Review | ISO [9-7.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | tbc | [6 empty] | SW | BS | Clarify if ML acceptance is needed?
| Dependent Failure Analysis (SW) Confirmation Review | ISO [2-6.5.5] | Volvo QDPR 8. (7.1) | New | NY | 0 |  |  |  | Phase C | tbc | [6 empty] | SW | BS
| Software Verification Report (Review) | ISO [6-7.5.4] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | [7 empty] | SW | BS/ML | Incl. ML acceptance
| Software unit design specification | ISO [6-8.5.1] |  | New | NY | 0 |  |  |  | Phase C | CW40/2026 | [6 empty] | SW | BS
| Software unit implementation | ISO [6-8.5.2] |  | New | NY | 0 |  |  |  | Phase C | CW40/2026 | [6 empty] | SW | BS
| Software unit verification specification (SWE.4) | ISO [6-9.5.1] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW40/2026 | [6 empty] | SW | BS
| Software unit verification specification (SWE.4) Verification Review | [16 empty] | SW | BS/ML | Clarify if ML acceptance is needed?
| Software unit verification report (SWE.4) | ISO [6-9.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW47/2026 | [6 empty] | SW | BS
| Software unit verification report (SWE.4) Verification Review | [16 empty] | FSM | BS/ML | Clarify if ML acceptance is needed?
| Software integration verification specification (SWE.5) | ISO [6-10.5.1] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW40/2026 | [6 empty] | SW | BS
| Software integration verification specification (SWE.5) Verification Review | [16 empty] | SW | BS/ML | Clarify if ML acceptance is needed?
| Software integration verification report (SWE.5) | ISO [6-10.5.3] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW47/2026 | [6 empty] | SW | BS
| Software integration verification report (SWE.5) Verification Review | [16 empty] | FSM | BS/ML | Clarify if ML acceptance is needed?
| Software qualification verification specification (SWE.6) | ISO [6-11.5.1] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW40/2026 | [6 empty] | SW | BS
| Software qualification verification specification (SWE.6) Verification Review | [16 empty] | SW | BS/ML | Clarify if ML acceptance is needed?
| Software qualification verification report (SWE.6) | ISO [6-11.5.2] | Volvo QDPR 8. (6.12) | New | NY | 0 |  |  |  | Phase C | CW47/2026 | [6 empty] | SW | BS
| Software qualification verification report (SWE.6) Verification Review | [16 empty] | FSM | BS/ML | Clarify if ML acceptance is needed?
| Configuration data specification (System) | ISO [6-C.5.1] |  | New | NY | 0 | [11 empty] | System | ML | Acc. RASIC
| Configuration data specification (SW) | ISO [6-C.5.1] | [15 empty] | SW | BS | Acc. RASIC
| Calibration data specification | ISO [6-C.5.2] |  | New | NY | 0 | [11 empty] | SW | ML | Acc. RASIC
| Configuration data | ISO [6-C.5.3] |  | New | NY | 0 | [11 empty] | SW | BS | Acc. RASIC
| Calibration data | ISO [6-C.5.4] |  | New | NY | 0 | [11 empty] | SW | ML | Acc. RASIC
| Verification specification (refined) | ISO [6-C.5.5] |  | New | NY | 0 | [11 empty] | SW | BS | Acc. RASIC
| Verification report (refined) | ISO [6-C.5.6] |  | New | NY | 0 | [11 empty] | SW | BS | Acc. RASIC
| Software architectural design specification (refined) | ISO [6-C.5.7] |  | New | NY | 0 | [11 empty] | SW | BS | Acc. RASIC
| Documentation of the software development environment (refined) | ISO [6-C.5.8] |  | New | NY | 0 | [11 empty] | SW | BS | Acc. RASIC
Production, operation, service and decommissioning
| Safety Production and Control Plan | ISO [2-7.5.1] ISO [4-6.5.5] ISO [5-7.5.4] ISO [7-5.5.1 – 4] ISO [7-6.5.1/2] | Volvo QDPR 8. (6.13) | New | NY | 0 |  |  |  | Phase D | CW35/2026 | [5 empty] | TSC POSD req's | FSM | BS | check APIS documents if compliant with ISO26262, else use BS templates
| Safety Production and Control Plan Verification Review | [16 empty] | FSM | ML | Incl. ML acceptance
| Process FMEA | ISO [7-5.4.1] | Volvo QDPR 8. (6.10) | New | NY | 0 |  |  |  | Phase C | CW35/2026 | [5 empty] | Process documentation | FSE | BS
| Process FMEA Verification Review | [16 empty] | FSE | ML | Incl. ML acceptance
| Safety Service Plan | ISO [7-5.5.5 – 5.5.10] | Volvo QDPR 8. (6.13) | New | NY | 0 |  |  |  | Phase D | CW50/2026 | [6 empty] | FSM | BS
| Safety Service Plan Verification Review | [16 empty] | FSM | ML | Incl. ML acceptance
| Field observation instructions | ISO [7-7.5.1] |  | New | NY | 0 |  |  |  | Phase D | CW50/2026 | [6 empty] | Production | ???
Supporting Processes
| Supplier selection report | ISO [8-5.5.1] |  | New | OK | 100 |  |  | Check with ML purchase team | Phase A | CW08/2026 | [6 empty] | PM | ML | Supplier self-assessment (BS)
| Configuration Management plan | ISO [8-7.5.1] |  | New | OK | 100 | Configuration Management Plan | 2.0 | https://erg-polarion-p1.mekra.net/polarion/#/project/11_P_01467_MEKRA_Vision_Controller/wiki/97_Configuration_Management/Configuration_Management_Plan | Phase A | CW08/2026 | [6 empty] | PM | ML
| Change Management plan | ISO [8-8.5.1] |  | New | DEV | 90 | Change Management Plan | 1.0 | https://erg-polarion-p1.mekra.net/polarion/#/project/11_P_01467_MEKRA_Vision_Controller/wiki/96_Change_Management/Change_Management_Plan | Phase A | CW08/2026 | [6 empty] | PM | ML
| Verification Plan/Specification/Report | ISO [8-9.5.1 – 3] |  | New | NOK | 0 |  |  |  | Phase A | CW08/2026 | [6 empty] | PM | ML | Clarify what is expectation?
| Documentation Management Plan | ISO [8-10.5.1] |  | New | NOK | 0 |  |  |  | Phase A | CW08/2026 | [6 empty] | PM | ML | Clarify what is expectation?
| Software tool criteria evaluation report (Systems+HW levels) | ISO [8-11.5.1] |  | New | OK | 100 |  |  | Check with J. Früh | Phase B | CW10/2026 | [6 empty] | FSM | ML
| Software tool criteria evaluation report (SW level) | ISO [8-11.5.1] |  | New | NOK | 0 |  |  |  | Phase B | CW10/2026 | [6 empty] | FSM | BS
| Software tool qualification report (Systems+HW level) | ISO [8-11.5.2] |  | New | OK | 100 |  |  | Check with J. Früh | Phase B | CW10/2026 | [6 empty] | FSM | ML
| Software tool qualification report (SW level) | ISO [8-11.5.2] |  | New | NOK | 0 |  |  |  | Phase B | CW10/2026 | [6 empty] | FSM | BS
| Software component documentation/ qualification report | ISO [8-12.5.1 – 3] |  | New | DEV | 50 |  |  |  | Phase C | CW31/2026 | [6 empty] | FSM | BS | Qualification of SW drivers (SerDes + Image Sensor)
| Hardware element evaluation plan/ test plan and report | ISO [8-13.5.1 – 3] |  | N/A | NA | 100 |  |  |  | N/A | N/A | [6 empty] | N/A | -
| Proven in use argument/analysis report | ISO [8-14.5.1/2] |  | N/A | NA | 100 |  |  |  | N/A | N/A | [6 empty] | N/A | -
Note on E1: Content to be changed in cover-sheet -> Base project ID
Note on L44: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Move 2 weeks in advance? To have 2 weeks for Review process
Note on N44: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Move 2 weeks in advance? To have 2 weeks for Review process
Note on O44: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Move 2 weeks in advance? To have 2 weeks for Review process
Note on L46: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Move 1 week in advance? To have 2 weeks for Review process
Note on N46: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Move 1 week in advance? To have 2 weeks for Review process
Note on O46: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Move 1 week in advance? To have 2 weeks for Review process
Note on L49: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Move 2 weeks in advance? To have 2 weeks for Review process
Note on N49: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Move 2 weeks in advance? To have 2 weeks for Review process
Note on O49: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Move 2 weeks in advance? To have 2 weeks for Review process
Note on L51: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Move 1 week in advance? To have 2 weeks for Review process
Note on N51: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Move 1 week in advance? To have 2 weeks for Review process
Note on O51: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Move 1 week in advance? To have 2 weeks for Review process

## Legend
OK | WP finished
DEV | Work product under development
NOK | Work product not started while due at current project phase
NY | Work product not yet due at current project phase
NA | Not applicable

## Schedule
Schedule
Month | [11 empty] | Jul'26 |  |  |  | Aug'26 |  |  |  |  | Sep'26 |  |  |  | Oct'26 |  |  |  | Nov'26 |  |  |  |  | Dec'26 |  |  | Jan'27 |  |  | Feb'27 |  |  |  | Mar'27 |  |  |  |  | Apr'27 |  |  |  | May'27 |  |  |  |  | Jun'26 |  |  |  | Jul'27 |  |  |  | Aug'27 |  |  |  |  | Sep'27
Week | [11 empty] | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
Date | [11 empty] | 6.7 | 13.7 | 20.7 | 27.7 | 3.8 | 10.8 | 17.8 | 24.8 | 31.8 | 7.9 | 14.9 | 21.9 | 28.9 | 5.10 | 12.10 | 19.10 | 26.10 | 2.11 | 9.11 | 16.11 | 23.11 | 30.11 | 7.12 | 14.12 | 21.12 | 11.1 | 18.1 | 25.1 | 1.2 | 8.2 | 15.2 | 22.2 | 1.3 | 8.3 | 15.3 | 22.3 | 29.3 | 5.4 | 12.4 | 19.4 | 26.4 | 3.5 | 10.5 | 17.5 | 24.5 | 31.5 | 7.6 | 14.6 | 21.6 | 28.6 | 5.7 | 12.7 | 19.7 | 26.7 | 2.8 | 9.8 | 16.8 | 23.8 | 30.8 | 6.9 | 13.9 | 20.9 | 27.9
Volvo Schedule + Projekt Milestones |  | Resp. | [8 empty] | End date
IPD P1 HW C-Sample | [10 empty] | KW44/26 | [16 empty] | ♦
System Design Freeze P1 | [10 empty] | KW27.5
System Test Freeze P1 | [10 empty] | KW32.5 |  |  |  |  | ♦
System Release P1 | [10 empty] | KW44.5 | [16 empty] | ♦
SW Design Freeze P1 | [10 empty] | KW29.5 |  | ♦
SW Test Freeze P1 | [10 empty] | KW31.5 |  |  |  | ♦
HW Design Freeze P1 | [10 empty] | KW29.5 |  | ♦
HW Test Freeze P1 | [10 empty] | KW31.5 |  |  |  | ♦
IPD P2 HW C-Sample | [10 empty] | KW8/27 | bar: Feb'27 8
System Design Freeze P2.2 | [10 empty] | KW39.5 | [11 empty] | ♦
System Test Freeze P2.2 | [10 empty] | KW47.5 | [19 empty] | ♦
System Release P2.2 | [10 empty] | KW06.5 | bar: Feb'27 6
SW Design Freeze P2.2 | [10 empty] | KW41.5 | [13 empty] | ♦
SW Test Freeze P2.2 | [10 empty] | KW43.5 | [15 empty] | ♦
HW Design Freeze P2.2 | [10 empty] | KW41.5 | [13 empty] | ♦
HW Test Freeze P2.2 | [10 empty] | KW44.5 | [16 empty] | ♦
IPD P3 HW C-Sample | [10 empty] | KW17/27 | bar: Apr'27 17
System Design Freeze P3 | [10 empty] | KW47.5 | [19 empty] | ♦
System Test Freeze P3 | [10 empty] | KW03.5 | bar: Jan'27 3
System Release P3 | [10 empty] | KW17.5 | bar: Apr'27 17
SW Design Freeze P3 | [10 empty] | KW52.5 | [24 empty] | ♦
SW Test Freeze P3 | [10 empty] | KW03.5 | bar: Jan'27 3
HW Design Freeze P3 | [10 empty] | KW52.5 | [24 empty] | ♦
HW Test Freeze P3 | [10 empty] | KW03.5 | bar: Jan'27 3
SOP | [10 empty] | KW37/27 | bar: Sep'27 37
Functional Safety Activities
Impact Analysis |  | ML
Impact Analysis Confirmation Review |  | ML
Safety Plan |  | BS
Safety Plan Confirmation Review |  | BS
Safety Plan Confirmation Review |  | ML
Safety Case |  | BS | bar: Feb'27 5 to Mar'27 10
Safety Case Confirmation Review |  | BS | bar: Mar'27 11 to Mar'27 12
Safety Case Confirmation Review |  | ML | bar: Mar'27 11 to Mar'27 12
Functional Safety Audit Report |  | BS | bar: Apr'27 14 to Apr'27 15
Functional Safety Assessment Plan |  | BS
Performance Audit/ Assessment |  | ML/BS | bar: Mar'27 9 to Mar'27 10
Functional Safety Assessment Report |  | BS | bar: Apr'27 14 to Apr'27 15
Release for Production Report |  | BS | bar: Jun'26 26 to Jul'27 27
Safety Goals - SOW2 | 13h | ML
Review | 4h | ML
Functional Safety Concept – SOW2 | 17h | ML
Functional Safety Concept - SOW2 Verification Review | 15h | ML
Functional Safety Concept - SOW2 Confirmation Review |  | BS
Technical Safety Concept – TSR's (incl. POSD) + Arch (incl. Verification Review) | Open WI: | ML/BS | MR | ME | AE | OJ | MV | AS | ES | AW | [5 empty] | Miro Vaca.
Amba Chip SW Safety Req - BIST TSRs | 10+x |  | 10 | x | [9 empty] | Arch |  | TSR + Arch
Review | 6+x |  | 6+x |  |  |  | x |  | 2+x
Amba Chip SW Safety Req - Clock TSRs | 3+x |  | 3 | x | [9 empty] | Rew + Arch |  | TSR + Arch
Review | 3+x |  | x | 3 |  |  | 3+x |  | 3+x
Amba Chip SW Safety Req - Power TSRs | x |  |  | x | [11 empty] | TSR + Arch
Review | 7+x |  | 7+x |  |  |  | 7+x |  | 3+x
Safety Goal Requirements - SG_1 TSRs | 7+x |  |  |  | 7+x | [8 empty] | Miro handover Chapter SG Req to Mohamed |  |  | TSR + Arch
Review | 7+x |  | tbd |  |  |  | tbd | tbd | tbd | tbd
Safety Goal Requirements - SG_2 TSRs | 14+x |  |  |  | 14+x | [11 empty] | TSR + Arch
Review | 14+x |  | tbd |  |  |  | tbd | tbd | tbd | tbd
Safety Goal Requirements - SG_3 TSRs | 12+x |  |  |  | 12+x | [11 empty] | TSR + Arch
Review | 12+x |  | tbd |  |  |  | tbd | tbd | tbd | tbd
Safety Goal Requirements - SG_4 TSRs | 11+x |  |  |  | 11+x | [11 empty] | TSR + Arch
Review | 11+x |  | tbd |  |  |  | tbd | tbd | tbd | tbd
DRAM Safety Requirements
Review | 11 |  | 11 |  |  |  | 2
Flash Safety Requirements
Review | 1 |  | 1
Deserializer Safety Requirements | 5 |  | 5 | [11 empty] | Rew + Arch |  | Rew + Arch
Review | 5 |  |  | 5 |  |  | 5 | 5
Ethernet PHY Safety Requirements | 6 + ? |  | 6 | [11 empty] | Rew + Arch |  | Rew + Arch
Review | 10 + ? |  |  | 4 |  |  | 4 | 9
PMIC Safety Requirements | 3 |  | 3 | [10 empty] | Rew + Arch |  |  | Rew + Arch
Review | 5 |  |  | 3 |  |  | 3 |  |  | 3
Safe State Requirements | 11 |  | 11 | [13 empty] | TSR + Arch
Review | 11 |  |  | tbd |  |  | tbd | tbd | tbd | tbd
Prod., Oper., Service and Dec. Requirements | ~10 |  | 1 | [20 empty] | TSR + Arch
Review | ~10 |  |  | tbd |  |  | tbd | tbd | tbd | tbd
Requirements Towards Vehicle | ~5 |  | 2 | [18 empty] | TSR + Arch
Review | ~5 |  |  | tbd |  |  | tbd | tbd | tbd | tbd
Requirements Towards SOW1 | ~5 | [20 empty] | TSR + Arch
Review | ~5
Temperature Sensing | ~15 | [18 empty] | TSR + Arch
Review | ~15
FuSa AE/AWB Requirements | ~30 | [16 empty] | TSR + Arch
Review | ~30
FuSa SOW1 configuration/requirements on SOW2 | ~90 | [12 empty] | TSR + Arch |  |  | Olli Vaca. |  | TSR + Arch
Review | ~90
FuSa Vehicle requirements on SOW2 | ~11 | [18 empty] | TSR | Arch
Review | ~11
Amba Safety Mechanism | 15+x
Review | 15+x
Identification of safety mechanism from Amba SW Safety Manual | 48 (HW) 34 (SW) | BS
Review |  | ML
Integration Safety Architectur into Sys Architecture |  | ML (A. Pasztor) | [24 empty] | ~ Start
Safety Architecture transfer EA to Polarion |  | ML (A. Pasztor)
Final linkage of Architectural elements |  | ML (A. Pasztor + M. Rekas?) | bar: Jan'27 2 to Jan'27 3
Hardware-Software Interface (HSI) Specification |  | ML/BS | [18 empty] | P2 | [8 empty] | P3
Technical Safety Concept Confirmation Review |  | BS
System FMEA (Component FMEA) |  | ML | [11 empty] | 40h
System FMEA Verification Review |  | ML
System FMEA Confirmation Review |  | BS
System FTA |  | BS
System FTA Verification Review |  | BS
System FTA Verification Review |  | ML | [26 empty] | 20h
System FTA Confirmation Review |  | BS
System Dependent Failure Analysis |  | BS
System Dependent Failure Analysis Verification Review |  | BS
System Dependent Failure Analysis Verification Review |  | ML | [26 empty] | 20h
System Dependent Failure Analysis Confirmation Review |  | BS
Integration and test strategy (SYS.4 & SYS.5) |  | BS
Integration and test strategy Confirmation Review |  | BS
Integration and test strategy Confirmation Review |  | ML (Team Aaron)
HW-SW Integration and test report (SYS.4) System Integration and test report (SYS.4)
Specification |  | BS
Specification Verification Review |  | BS
Specification Verification Review |  | ML (Team Aaron)
Execution & reporting |  | BS
Execution & reporting (Pre-Testing)
Execution & reporting Verification Review |  | ML (Team Aaron)
Integrated System test report (SYS.5)
Specification |  | BS
Specification Verification Review |  | BS
Specification Verification Review |  | ML (Team Aaron)
Execution & reporting |  | BS | bar: Jan'27 2 to Jan'27 4
Execution & reporting Verification Review |  | ML (Team Aaron) | bar: Jan'27 3 to Feb'27 5
MEKRA Joint Review 1 (consistency check) |  | ML
MEKRA Joint Review 2 (consistency check) |  | ML | bar: Feb'27 6 to Feb'27 8
MEKRA Joint Review 3 (consistency check) |  | ML | bar: Apr'27 15 to Apr'27 17
Hardware Safety Requirements Specification (HWSRS) |  | BS | [20 empty] | P2 | [9 empty] | P3
Hardware Safety Requirements verification report |  | BS/ML
Hardware-software interface (HSI) specification (refined) |  | BS/ML
Hardware design specification |  | ML
Hardware design verification report |  | ML
Qualitative HW Safety Analysis (HW FMEA) |  | -
Quantitative HW Safety Analysis (HW FMEDA) |  | BS
Quantitative HW Safety Analysis (HW FMEDA) Verification Review | 30h | BS/ML
Quantitative HW Safety Analysis (HW FMEDA) Confirmation Review |  | BS
Analysis of the effectiveness of the architecture of the item to cope with the random hardware failures |  | BS
Analysis of the effectiveness of the architecture of the item to cope with the random hardware failures Verification Review |  | BS
Analysis of safety goal violations due to random hardware failures |  | BS
Analysis of safety goal violations due to random hardware failures Verification Review |  | BS
Specification of dedicated measures for hardware |  | BS
Hardware integration and verification specification |  | ML
Hardware integration and verification specification Verification Review |  | ML/BS
Hardware integration and verification report |  | ML/BS
Hardware integration and verification report Verification Review |  | ML
Documentation of the software development environment |  | BS
Software Safety Requirements Specification (SWSRS) |  | BS
Hardware-software interface (HSI) specification (refined) |  | BS/ML
Software Verification Report (Review) |  | BS/ML
Software architectural design specification |  | BS/ML
Qualitative SW Safety Analysis (SW FMEA) |  | BS
Qualitative SW Safety Analysis (SW FMEA) Verification Review |  | BS/ML
Qualitative SW Safety Analysis (SW FMEA) Confirmation Review |  | BS
Dependent Failure Analysis (SW) |  | BS
Dependent Failure Analysis (SW) Verification Review |  | BS
Dependent Failure Analysis (SW) Confirmation Review |  | BS
Software Verification Report (Review) |  | BS/ML
Software unit design specification |  | BS
Software unit implementation |  | BS
Software unit verification specification (SWE.4) |  | BS
Software unit verification specification (SWE.4) Verification Review |  | BS/ML
Software unit verification report (SWE.4) |  | BS
Software unit verification report (SWE.4) Verification Review |  | BS/ML
Software integration verification specification (SWE.5) |  | BS
Software integration verification specification (SWE.5) Verification Review |  | BS/ML
Software integration verification report (SWE.5) |  | BS
Software integration verification report (SWE.5) Verification Review |  | BS/ML
Software qualification verification specification (SWE.6) |  | BS
Software qualification verification specification (SWE.6) Verification Review |  | BS/ML
Software qualification verification report (SWE.6) |  | BS
Software qualification verification report (SWE.6) Verification Review |  | BS/ML
SW Drop (Pre-Testing)
SW Drop
Configuration data specification (System) |  | ML
Configuration data specification (SW) |  | BS
Calibration data specification |  | ML
Configuration data |  | BS
Calibration data |  | ML
Verification specification (refined) |  | BS
Verification report (refined) |  | BS
Software architectural design specification (refined) |  | BS
Documentation of the software development environment (refined) |  | BS
Safety Production and Control Plan |  | BS
Safety Production and Control Plan Verification Review |  | ML
Process FMEA |  | BS
Process FMEA Verification Review |  | ML
Safety Service Plan |  | BS
Safety Service Plan Verification Review |  | ML
Field observation instructions |  | ???
Supplier selection report |  | ML
Configuration Management plan |  | ML
Change Management plan |  | ML
Verification Plan/Specification/Report |  | ML
Documentation Management Plan |  | ML
Software tool criteria evaluation report (Systems+HW levels) |  | ML
Software tool criteria evaluation report (SW level) |  | BS
Software tool qualification report (Systems+HW level) |  | ML
Software tool qualification report (SW level) |  | BS
Software component documentation/ qualification report |  | BS
Tranfer to Predefined (add Approver + Verif. Method/Criteria)
=> Revisit for potential updates
Note on T3: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Prefered joint review by Test Team (caused by WS in CW35) No offline review possible du to WS
Note on H50: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Re-Review Marc kann niedriger Priorisiert werden (Wenn bereits Approved wurde und Req aufgrund Disaaproval von anderer Person disapproved wurde)
Note on B51: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Review Meeting in cw33
Note on Q51: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Potentiell hoher Klärungsaufwand mit Amba
Note on O53: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: 3x Disapproved (Miro rework) Problem: Input Amba fehlt!!!! Eskalation über JIRA Tickets (Blocker) => wird über Management meeting verfolgt
Note on Q53: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Potentiell hoher Klärungsaufwand mit Amba
Note on B55: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Review Meeting in cw33
Note on Q55: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Potentiell hoher Klärungsaufwand mit Amba
Note on B66: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Offline work requested
Note on B68: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Offline work requested
Note on D69: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Offline Rework Miro needed
Note on B71: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Chapter will be completely reworked by Assignee 1) Transfer Req to Polarion 2) Check if available Req need to be rejected 3) Start approval process
Note on D73: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Offline Rework Miro needed
Note on A87: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Paket O. Jeaschke
Note on A93: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Erstellung aller notwendigen TSR‘s, falls FMEA im Nachgang die Notwendigkeit nicht belegt, dann rejecten im Nachgang
Note on P93: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: - 15 Req to implement => will be added to Polarion as Draft (still review with Miro needed) - Add to correct chapter or implement new chapter (Open -> to review Elbeih & Miro) - 15 Req to be analyzed (Open -> to review Elbeih & Miro & HW/SW & Amba) =>On 13./27.07 initiated JIRA Tickets (8x) for Questions on Amba (378 - 389 [only Safety ones])
Note on C98: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Not a separate HSI for Safety. HSI is in lead of System Team. => FUSA Team needs to bring their Input into the existing documentation
Note on AB103: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: To be shifted after completion of TSR‘s & Safety Architecture
Note on AB107: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: To be shifted after completion of TSR‘s & Safety Architecture
Note on A136: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Update will be provided by Elbeih