## Open-Points-List
Open-Point-List - Functional Safety Management
| Projectnumber: | 11-E-01405 | [9 empty] | Status: CW 33/2026
| Projectname: | SOW2 - Rear and Trailer Camera RFP - Volvo
MEKRA - Brightskies
Topics |  |  | Responsible |  |  | Status & follow up
No. | Measure | defined on: | Name | Agreed with (support) | Completion until | Status: defined in work done rejected |  |  |  | Next review: | Done on: | Comments
[6 empty] | 25% | 50% | 75% | 100%
1 | Release Safety Plan | 2026-08-05
1.1 | Define responsible Person as "FuSa Auditor" | 2026-08-05 | N. Hügel | [8 empty] | 13.08.2026: To ask Hend (as an official request by ML)
1.2 | Remove "Table of Activities" and refer only to "Safety Case Appendix" | 2026-08-05 | N. Hügel |  |  | done |  |  |  |  | 2026-08-07
1.3 | Consider all methods which are listed by ISO 26262 => Sheet "See List of methodes" | 2026-08-05 | -
1.3.1 | Part 4 (SYS) | 2026-08-05 | N. Hügel |  |  | done |  |  |  |  | 2026-08-07 | 07.08.2026: Refered from Safety Plan to Test Plan
1.3.2 | Part 5 (HW) | 2026-08-05 | N. Hügel | [8 empty] | 07.08.2026: 1) Reference added to table 1-3 2) Definition of methods of table 10-12 to be defined in HW Test Strategy (@Henry)
1.3.3 | Part 6 (SW) => Update complete content of Chapter 7 "SW-Level" | 2026-08-05 | M. Elbeih | [8 empty] | 07.08.2026: Descriptions to be added by BS, including reference to methods according ISO (table 1 – 15) and SW Test Strategies/ Plans.
1.4 | Functional Audit Report for Sub-Supplier (Brightskies) available or to be planned in near future? | 2026-08-13 | M. Elbeih
2 | Release FuSa Assessment Plan | 2026-08-05
2.1 | Define Safety Assessor & Assistant | 2026-08-05 | N. Hügel | [8 empty] | 13.08.2026: To ask Hend (as an official request by ML)
2.2 | Define Safety manager | 2026-08-05 | M. Elbeih |  |  | done |  |  |  |  | 2026-08-13 | 05.08.2026: Should be defined as already defined in the "Functional Safety Plan" ---- Functional Safety Manager (MEKRA): Niklas Hügel ---- Project Functional Safety Manager (BS): Mohamed Elbeih
2.3 | Define Budget and costs | 2026-08-05 | M. Elbeih |  |  | done |  |  |  |  | 2026-08-13 | 05.08.2026: You can fill in this statement: "….costs are covered by MEKRA. The assessment will be part of a MEKRA purchase order to Brightskies"
2.4 | Defne the Safety assessment process | 2026-08-05 | M. Elbeih | [8 empty] | 13.08.2026: M. Elbeih to clarify with his manager.
3 | Clarification on FUSA related Production process topics 1) P-FMEA 2) Prod Requirements (TSR's) 3) Production Control Plan | 2026-08-05 | N. Hügel
4 | Release HSI (including FUSA) 1) Clarify with System Lead how to progress (Meeting needed: Miro, Elbeih, Igor/Alexander, Elshal) | 2026-08-05 | M. Elbeih
5
6
7
8
9
10
11
12
13

## List of methods - 4
Part | Chapter | Table | Name
4 | 6.4.4 | 1 | System architectural design analysis
Not ASIL dependent
4 | 6.4.9 | 2 | Verification
Not ASIL dependent
4 | 7.4.1 | 3 | Methods for deriving test cases for integration testing
Not ASIL dependent
4 | 7.4.2 | 4 | Correct implementation of technical safety requirements at the hardware-software level
Not ASIL dependent
4 | 7.4.2 | 5 | Correct functional performance, accuracy and timing of safety mechanisms at the hardware-software level
ASIL (A), B, C, D
4 | 7.4.2 | 6 | Consistent and correct implementation of external and internal interfaces at the hardware-software level
ASIL (A), B, C, D
4 | 7.4.2 | 7 | Effectiveness of a safety mechanisms at the hardware-software level
ASIL (A), (B), C, D
4 | 7.4.2 | 8 | Level of robustness at the hardware-software level
ASIL (A), (B), (C), D
4 | 7.4.3 | 9 | Correct implementation of functional safety and technical safety requirements at the system level
Not ASIL dependent
4 | 7.4.3 | 10 | Correct functional performance, accuracy and timing of safety mechanisms at the system level
ASIL (A), (B), (C), D
4 | 7.4.3 | 11 | Consistent and correct implementation of external and internal interfaces at the system level
Not ASIL dependent
4 | 7.4.3 | 12 | Level of robustness at the system level
Not ASIL dependent
4 | 7.4.4 | 13-16 | In response of OEM

## List of methods - 5
Part | Chapter | Table | Name
5 | 7.4.1 | 1 | Properties of hardware architectural design
Not ASIL dependent
5 | 7.4.3 | 2 | Hardware design safety analysis
Not ASIL dependent
5 | 7.4.4 | 3 | Hardware design verification
Not ASIL dependent
5 | 10.4.4 | 10 | Methods for deriving test cases for hardware integration testing
Not ASIL dependent
5 | 10.4.5 | 11 | Hardware integration tests to verify the completeness and correctness of the implementation of the hardware safety requirements
Not ASIL dependent
5 | 10.4.6 | 12 | Hardware integration tests to verify durability, robustness and operation under stresses
Not ASIL dependent

## List of methods - 6
Part | Chapter | Table | Name
6 | 5.4.2 | 1 | Topics to be covered by modelling and coding guidelines
Not ASIL dependent
6 | 7.4.1 | 2 | Notations for software architectural design
Not ASIL dependent
6 | 7.4.3 | 3 | Principles for software architectural design
Not ASIL dependent
6 | 7.4.14 | 4 | Methods for the verification of the software architectural design
Not ASIL dependent
6 | 8.4.3 | 5 | Notations for software unit design
Not ASIL dependent
6 | 8.4.5 | 6 | Design principles for software unit design and implementation
Not ASIL dependent
6 | 9.4.2 | 7 | Methods for software unit verification
Not ASIL dependent
Not ASIL dependent
6 | 9.4.3 | 8 | Methods for deriving test cases for software unit testing
Not ASIL dependent
6 | 9.4.4 | 9 | Structural coverage metrics at the software unit level
Not ASIL dependent
6 | 10.4.2 | 10 | Methods for verification of software integration
Not ASIL dependent
6 | 10.4.3 | 11 | Methods for deriving test cases for software integration testing
Not ASIL dependent
6 | 10.4.5 | 12 | Structural coverage at the software architectural level
ASIL (A), (B), C, D
6 | 11.4.1 | 13 | Test environments for conducting the software testing
Not ASIL dependent
6 | 11.4.2 | 14 | Methods for tests of the embedded software
Not ASIL dependent
6 | 11.4.3 | 15 | Methods for deriving test cases for the test of the embedded software
Not ASIL dependent

## List of methods - 8
Part | Chapter | Table | Name
8 | 6.4.1 | 1 | Specifying safety requirements
Not ASIL dependent
8 | 6.4.2 | 2 | Methods for the verification of safety requirements
Not ASIL dependent
8 | 11.4.6 | 4 | Qualification of software tools classified TCL3
Not ASIL dependent
8 | 11.4.6 | 5 | Qualification of software tools classified TCL2
Not ASIL dependent